# Alta Flatirons — Project Status Report

Mile High Metal Works · Wood Partners · Status as of April 29, 2026

# Project at a glance

24 of 30 release packages delivered & installed (80% complete)

84% of fabrication scope complete (663 of 793 shop hours)

73% of installation scope complete (721 of 990 field hours)

14 submittals currently in review

Project Manager: Gary Almeida

# Headline observations

4 of 6 in-flight packages have install targets that are more aggressive than the company-wide typical pace (negative ETA Δ). The team is pacing toward tighter-than-typical promises and is largely hitting them — Alta continues to run faster than average across the company's project history.

2 packages are past their target install date (#433, #511). These are the highest-priority items to triage.

1 package is past the latest-reasonable historical pace (#289) — this has been in production longer than 90% of comparable packages and warrants a closer look at what's blocking it.

5 submittals have exceeded the latest-reasonable review window and need re-engagement (idle 100+ days in several cases).

3 submittals are stretching past the typical review window — watch list for the next two weeks.

# Project timeline

First submittal issued: June 12, 2025 (~11 months ago)

First fabrication release: September 18, 2025 (~7 months ago)

First package delivered: April 9, 2026

# Submittals

To date, 108 submittal records have moved through the Procore submittal log on this project. 94 are closed or issued for construction; 14 are currently active in review.

## Active submittals — expected close vs. on-time status

Each submittal's expected close is calculated from its open date plus our company-wide review-cycle data: a typical close (median of past reviews) and a latest reasonable close (90th-percentile, i.e. only 10% take longer).

> Cycle benchmarks: **GC Approval**: typical 21 days · latest reasonable 48 days (n=60 historical) · **Drafting Release Review**: typical 15 days · latest reasonable 40 days (n=246 historical)

| Submittal | With | Type | Opened | Days open | Typical close | Latest reasonable | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Structural Steel Beams Area 3 | Gary Almeida | GC Approval | Dec 15 | 135d | Jan 5 | Feb 1 | 🔴 Overdue |
| ADD/ALT Standard Bike Rack | Gary Almeida | GC Approval | Dec 15 | 135d | Jan 5 | Feb 1 | 🔴 Overdue |
| Stair Core 5 | Colton Arendt | Drafting Release Review | Jan 5 | 114d | Jan 20 | Feb 14 | 🔴 Overdue |
| Stair Core 3 | Rourke Alvarado | Drafting Release Review | Jan 5 | 114d | Jan 20 | Feb 14 | 🔴 Overdue |
| Stair Core 4 | Gary Almeida | Drafting Release Review | Jan 5 | 114d | Jan 20 | Feb 14 | 🔴 Overdue |
| Area 2 remaining steel | David Servold | Drafting Release Review | Apr 7 | 22d | Apr 22 | May 17 | ⚠ Stretching |
| Stair Core 6 | Colton Arendt | Drafting Release Review | Apr 13 | 16d | Apr 28 | May 23 | ⚠ Stretching |
| Balcony Guardrail | Colton Arendt | GC Approval | Apr 7 | 22d | Apr 28 | May 25 | ⚠ Stretching |
| B11 replacment | David Servold | Drafting Release Review | Apr 14 | 15d | Apr 29 | May 24 | On track |
| Stair Core 3 lvl 1 | Gary Almeida | Drafting Release Review | Apr 16 | 13d | May 1 | May 26 | On track |
| B14 and B15 | Dustin Pauley | Drafting Release Review | Apr 24 | 5d | May 9 | Jun 3 | On track |
| Area 2 Column splice | David Servold | GC Approval | Apr 20 | 9d | May 11 | Jun 7 | On track |
| Pergola Structures | Dalton Rauer | GC Approval | Apr 27 | 2d | May 18 | Jun 14 | On track |
| Trash Chute Support Angles | David Servold | GC Approval | Apr 28 | 1d | May 19 | Jun 15 | On track |

# Fabrication & delivery status

24 of 30 release packages have been delivered and installed. The remaining packages are at the following stages:

| Phase | Packages |
| --- | --- |
| In fabrication | 2 |
| Final QC | 2 |
| In paint | 1 |
| Ready for shipping | 1 |
| Delivered & installed | 24 |

## Packages currently in production

Each package is benchmarked against company-wide release pace: typical release-to-delivery is 41 days, latest reasonable is 98 days (n=160 historical). The ETA Δ column shows the difference between the originally targeted install date and the typical-pace projection — positive means the target gave us margin, negative means it was faster than typical.

| Package | Description | Phase | Released | Days open | Target install | Typical close | Latest reasonable | ETA Δ | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| #289 | RFI 74 Double Wall Hold Down Embeds | In fabrication | Jan 16 | 103d | May 12 | Feb 26 | Apr 24 | +75d | 🔴 Overdue |
| #433 | Hold Down Embed Install Area 4 | Ready for shipping | Mar 9 | 51d | Apr 16 | Apr 19 | Jun 15 | -3d | ⚠ Stretching |
| #430 | Area 4 Structural Steel | In paint | Mar 11 | 49d | May 6 | Apr 21 | Jun 17 | +15d | ⚠ Stretching |
| #511 | Retail Lvl 2 Holdowns | Final QC | Apr 6 | 23d | Apr 23 | May 17 | Jul 13 | -24d | On track |
| #560 | RFI #139 Elev 2 & Retail Mechanical Shaf | In fabrication | Apr 21 | 8d | May 7 | Jun 1 | Jul 28 | -25d | On track |
| #552 | Garage CMU TOW Connection | Final QC | Apr 16 | 13d | May 14 | May 27 | Jul 23 | -13d | On track |

## Recently delivered (last 30 days)

| Package | Description | Released | Delivered |
| --- | --- | --- | --- |
| #434 | Hold Down Embed Install Area 5 | Mar 9 | Apr 23 |
| #437 | CO#04 Additional HD Embeds | Mar 10 | Apr 23 |
| #510 | HD19 Strap | Apr 6 | Apr 23 |
| #435 | Hold Down Embed Install Area 6 | Mar 9 | Apr 23 |
| #493 | CO#07 Additional HD Embeds 2 | Mar 30 | Apr 16 |
| #408 | Area 3 Structural Steel | Apr 9 | Apr 16 |
| #389 | Area 2 Structural Steel.389 S1 | Mar 5 | Apr 14 |
| #294 | Area 6 Structural Steel | Feb 17 | Apr 9 |
| #431 | Hold Down Embed Install Area 2 | Mar 9 | Apr 9 |
| #432 | Hold Down Embed Install Area 3 | Mar 9 | Apr 9 |
| #V547 | EP1 Embeds | Mar 31 | Apr 9 |
| #495 | Area 6 Extended Clips | Apr 1 | Apr 9 |

# Items needing attention

Package #433 — Hold Down Embed Install Area 4: target install Apr 16, now 13 days past target. Currently in ready for shipping; typical-pace projection has been Apr 19.

Package #511 — Retail Lvl 2 Holdowns: target install Apr 23, now 6 days past target. Currently in final qc; typical-pace projection has been May 17.

5 submittals are past the latest-reasonable close window — these need re-engagement: Structural Steel Beams Area 3, ADD/ALT Standard Bike Rack, Stair Core 5, Stair Core 3, Stair Core 4

Forecast methodology: Expected close dates are derived from this project's own review and fabrication pace to date. Each estimate gives a typical-case date and a latest-case date based on the actual time similar items have taken on this project.