## Sheet1
Job # | Release # | Job | Description | Fab Hrs | Install HRS | Paint color | PM | BY | Released | Fab Order | Cut start | Fitup comp | Welded | Paint Comp | Ship | Start install | Comp. ETA | Job Comp | Notes
200 | 879 | TCR - Alexan Diagonal | Bldg 3 Stair 2 | 81.2684 | 123.9125 | Red Oxide Primed | DR | CBA | 2024-10-18 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-08 | 0.9 | All but WHR
320 | 373 | Thompson Thrift - Landing at Lemay | Bilding 1 Patio & Balcony Ultralox Rails P1 of 2 | 9.1556 | 106.5556 | Factory Black | DR | CBA | 2025-04-23 | 1 | X | X | X | X | X | 2025-06-10 | 2025-06-18 | 0.5
340 | 419 | AMLI - Littleton Village II | Garage Bollards | 18 | 18 | Safety Yellow | DR | DCR | 2025-05-14 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-31 | O | QC Done
130 | 271 | Fairfield - Arista Fairfield | Bld 8 Balcony Rails | 84.9786 | 60.25 | Railing Black | GA | DCR | 2025-02-26 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-04 | 0.9 | QC Done
130 | 421 | Fairfield - Arista Fairfield | Typ Awning | 516 | 516 | Railing Black | GA | DCR | 2024-01-18 | 1 | X | X | X | X | X | 2025-07-30 | 2025-09-12 | 0.8 | Bld 14, 1-11 complete Clubhouse
130 | 430 | Fairfield - Arista Fairfield | Steel Canopies | 610.5 | 697.5 | Red-ox prime | GA | DCR | 2024-01-31 | 1 | X | X | X | X | X | 2025-07-30 | 2025-09-29 | 0.8 | Bld 14, CH comp 1-11 , 1-6 brackets installed
130 | 279 | Fairfield - Arista Fairfield | Bike Racks | 14 | 28 | Pre Galv. Finish | GA | DTS | 2025-03-03 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-31 | O | 5 of 28 installed
130 | 323 | Fairfield - Arista Fairfield | Bld 9 Balcony Rails | 95.8212 | 70.5 | Railing Black | GA | DCR | 2025-03-25 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-05 | O
130 | 358 | Fairfield - Arista Fairfield | Bld 11 Balcony Rails | 84.9786 | 60.25 | Railing Black | GA | DCR | 2025-04-08 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-04 | O | QC Done
130 | 359 | Fairfield - Arista Fairfield | Bldg 11 Roof Access Ladder | 3 | 3 | Railing Black | GA | SDO | 2025-04-11 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-30 | O | QC Done
130 | 417 | Fairfield - Arista Fairfield | Bld 12 Stair 1-4 ,south stairs, cane rails | 25 | 20 | Railling Black 38/81009 | GA | CBA | 2025-05-14 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-31 | O | QC Done
130 | 427 | Fairfield - Arista Fairfield | Remaining Balcony Rails | 50 | 0 | Railing Black | GA | DCR | 2025-05-23 | 1 | X | X | X | X | X | 2025-06-04 | 2025-06-04 | O | QC Done
130 | 416 | Fairfield - Arista Fairfield | Bld 12 Balcony Rails | 138.9465 | 100.25 | Railing Black | GA | DCR | 2025-05-15 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-07 | O | QC Done
130 | 391 | Fairfield - Arista Fairfield | Awning KP's | 10 | 0 | Railing Black | GA | DCR | 2025-04-23 | 1 | X | X | X | X | X | 2025-05-20 | 2025-05-20 | O | QC Done
190 | 892 | Hinton - Metro Center | Bld 1 Balcony Guardrail | 88.25 | 88.25 | Railing Black | GA | DCR | 2025-01-16 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-06 | 0.5 | QC Done
190 | 278 | Hinton - Metro Center | Stair Core 4A | 63.9284 | 61.65 | Red Oxide Primed | GA | DCR | 2025-02-28 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-04 | 0.9 | All but WHR
190 | 222 | Hinton - Metro Center | Bld 2 Roof Access Ladder | 0 | 6.5 | Red Oxide Primed | GA | DCR | 2025-02-20 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-30 | O
190 | 863 | Hinton - Metro Center | Stair Core 3A | 74.6101 | 73.6 | Red Oxide Primed | GA | DCR | 2024-09-16 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-05 | 0.9 | All but WHR
190 | 861 | Hinton - Metro Center | Stair Core 3B | 72.6349 | 71.55 | Red Oxide Primed | GA | DCR | 2024-09-16 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-05 | 0.9 | All but WHR
190 | 337 | Hinton - Metro Center | Stair Core 5B | 83.804 | 82.65 | Red Oxide Primed | GA | DCR | 2025-03-28 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-06 | 0.9 | All but WHR
190 | 320 | Hinton - Metro Center | Stair Core 5A | 83.804 | 82.65 | Red Oxide Primed | GA | DCR | 2025-03-18 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-06 | 0.9 | All but WHR
190 | 335 | Hinton - Metro Center | Stair Core 3B Lvl 1-2 | 35.8707 | 8 | Red Oxide Primed | GA | DCR | 2025-03-28 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-30 | 0.9 | All but WHR
190 | 334 | Hinton - Metro Center | Stair Core 3A Lvl 1-2 | 30.7707 | 8 | Red Oxide Primed | GA | DCR | 2025-03-28 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-30 | 0.9 | All but WHR
190 | 176 | Hinton - Metro Center | Stair Core 5C | 63.9284 | 61.65 | Red Oxide Primed | GA | DCR | 2024-12-24 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-04 | 0.9 | All but WHR
190 | 167 | Hinton - Metro Center | Stair Core 4B | 64.178 | 63.4 | Red Oxide Primed | GA | DCR | 2024-12-23 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-04 | 0.9 | All but WHR
190 | 678 | Hinton - Metro Center | Stair Core 1B | 64.178 | 63.4 | Red Oxide Primed | GA | DCR | 2024-06-05 | 1 | X | X | X | X | X | 2024-07-07 | 2024-07-10 | 0.9 | All but WHR
190 | 677 | Hinton - Metro Center | Stair Core 1A | 64.178 | 63.4 | Red Oxide Primed | GA | DCR | 2024-06-05 | 1 | X | X | X | X | X | 2024-06-28 | 2024-07-03 | 0.9 | All but WHR
190 | 848 | Hinton - Metro Center | Stair Core 2C | 64.178 | 63.4 | Red Oxide Primed | GA | DCR | 2024-09-16 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-04 | 0.9 | All but WHR
190 | 862 | Hinton - Metro Center | Stair Core 3C | 64.178 | 63.4 | Red Oxide Primed | GA | DCR | 2024-09-16 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-04 | 0.9 | All but WHR
190 | 847 | Hinton - Metro Center | Stair Core 2B | 68.0162 | 65.85 | Red Oxide Primed | GA | DCR | 2024-09-16 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-05 | 0.9 | All but WHR
380 | 388 | Brinkman - Marshall Pointe | Elevator Hoist Beams | 10.73 | 0.1746 | Red Oxide Primed | GA | SDO | 2025-04-23 | 1 | X | X | X | X | X | 2025-05-14 | 2025-05-14 | O | QC Done
170 | 131 | Garrett -Banyan High Point | Bld 2 Stair B | 38.702 | 38.1 | Red Oxide Primed | RL | DCR | 2024-12-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-01 | 0.9 | QC Done
170 | 130 | Garrett -Banyan High Point | Bld 2 Stair A | 38.702 | 38.1 | Red Oxide Primed | RL | DCR | 2024-12-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-01 | 0.9 | QC Done
170 | 147 | Garrett -Banyan High Point | Bld 6 Stair B | 38.702 | 38.1 | Red Oxide Primed | RL | DCR | 2024-12-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-01 | 0.9 | All but WHR
170 | 132 | Garrett -Banyan High Point | Bld 3 Stair A | 38.702 | 38.1 | Red Oxide Primed | RL | DCR | 2024-12-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-01 | 0.9 | All but WHR
170 | 141 | Garrett -Banyan High Point | Bld 3 Stair B | 38.702 | 38.1 | Red Oxide Primed | RL | DCR | 2024-12-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-01 | 0.9 | All but WHR
170 | 146 | Garrett -Banyan High Point | Bld 6 Stair A | 38.702 | 38.1 | Red Oxide Primed | RL | DCR | 2024-12-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-01 | 0.9 | All but WHR
170 | 145 | Garrett -Banyan High Point | Bld 5 Stair B | 38.702 | 38.1 | Red Oxide Primed | RL | DCR | 2024-12-06 | 1 | X | X | X | X | X | 2025-04-28 | 2025-04-30 | 0.9 | QC Done
170 | 144 | Garrett -Banyan High Point | Bld 5 Stair A | 38.702 | 38.1 | Red Oxide Primed | RL | DCR | 2024-12-06 | 1 | X | X | X | X | X | 2025-04-25 | 2025-04-29 | 0.9 | All but WHR
170 | 128 | Garrett -Banyan High Point | Bld 1 Stair A | 58.0654 | 57.25 | Red Oxide Primed | RL | DCR | 2024-12-05 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-04 | 0.9 | All but WHR
170 | 129 | Garrett -Banyan High Point | Bld 1 Stair B | 60.7906 | 60.05 | Red Oxide Primed | RL | DCR | 2024-12-05 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-04 | 0.9 | All but WHR
170 | 142 | Garrett -Banyan High Point | Bld 4 Stair A | 38.702 | 38.1 | Red Oxide Primed | RL | DCR | 2024-12-06 | 1 | X | X | X | X | X | 2025-02-10 | 2025-02-12 | 0.9 | All but WHR
170 | 143 | Garrett -Banyan High Point | Bld 4 Stair B | 38.702 | 38.1 | Red Oxide Primed | RL | DCR | 2024-12-06 | 1 | X | X | X | X | X | 2025-02-10 | 2025-02-12 | 0.9 | All but WHR
330 | V243 | Brinkmann - Aspendale Littleton Senior | Beam # 18 | 5 | 1.5 | Red Oxide Primer | RL | RL | 2025-06-09 | 1 | X | X | X | X | X | 2025-06-16 | 2025-06-16 | O | Fabrication Error. Beam ordered 6/9.
330 | 277 | Brinkmann - Aspendale Littleton | Structural Steel | 275.7061 | 397.9245 | TBD | RL | DTS | 2025-03-04 | 1 | X | X | X | X | X | 2025-03-31 | 2025-05-02 | 0.9 | QC Done
400 | 336 | Mountain West Contractors - Fieldhouse (Idaho Springs) | Building 3 Stair Core 5 | 53.6906 | 52.5 | Railing Black | RL | SDO | 2025-04-02 | 1 | X | X | X | X | X | 2025-04-29 | 2025-05-02 | 0.9 | All but WHR
400 | 340 | Mountain West Contractors - Fieldhouse (Idaho Springs) | Building 3 Stair Core 6 | 77.3292 | 75.1 | Railing Black | RL | SDO | 2025-04-07 | 1 | X | X | X | X | X | 2025-04-29 | 2025-05-05 | 0.9 | All but WHR
400 | 368 | Mountain West Contractors - Fieldhouse (Idaho Springs) | Building 2 Stair Core 3 | 53.978 | 52.55 | Railing Black | RL | SDO | 2025-04-16 | 1 | X | X | X | X | X | 2025-05-12 | 2025-05-15 | 0.9 | All but WHR
400 | 372 | Mountain West Contractors - Fieldhouse (Idaho Springs) | Building 2 Stair Core 4 | 61.728 | 59.55 | Railing Black | RL | SDO | 2025-04-18 | 1 | X | X | X | X | X | 2025-05-12 | 2025-05-15 | 0.9 | All but WHR
400 | 364 | Mountain West Contractors - Fieldhouse (Idaho Springs) | Building 1 Stair Core 1 | 35.9207 | 34.85 | Railing Black | RL | SDO | 2025-04-21 | 1 | X | X | X | X | X | 2025-05-28 | 2025-05-30 | 0.9 | All but WHR
400 | 367 | Mountain West Contractors - Fieldhouse (Idaho Springs) | Building 1 Stair Core 2 | 43.102 | 41.55 | Railing Black | RL | SDO | 2025-04-21 | 1 | X | X | X | X | X | 2025-05-28 | 2025-05-30 | 0.9 | All but WHR
900 | 210 | Arlington - Velo Interlocken | Elevator Pit Ladder | 31.5 | 28 | Red Oxide Primed | RL | SDO | 2025-01-27 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-31 | O | QC Done
900 | 408 | Arlington - Velo Interlocken | Standpipe Protection | 75 | 60 | Red Oxide Primed | RL | DCR | 2025-05-05 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-04 | O
900 | 979 | Arlington - Velo Interlocken | Bld 2 Balconies | 145.7248 | 124 | Railing Black | RL | DCR | 2024-11-19 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-08 | 0.9 | QC Done
900 | 218 | Arlington - Velo Interlocken | Bld 3 Balconies | 147.087 | 122.5 | Railing Black | RL | DCR | 2025-02-03 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-08 | 0.75 | Wait to ship
900 | 217 | Arlington - Velo Interlocken | Bld 4 Balconies | 147.4876 | 125.5 | Railing Black | RL | DCR | 2025-01-30 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-08 | 0.5 | Wait to ship
900 | 799 | Arlington - Velo Interlocken | Bld 5 Stair Core 1 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-06 | 0.9 | All but WHR
900 | 800 | Arlington - Velo Interlocken | Bld 5 Stair Core 2 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-06 | 0.9 | All but WHR
900 | 802 | Arlington - Velo Interlocken | Bld 6 Stair Core 2 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2024-12-19 | 2024-12-26 | 0.9 | All but WHR
900 | 801 | Arlington - Velo Interlocken | Bld 6 Stair Core 1 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2024-12-19 | 2024-12-26 | 0.9 | All but WHR
900 | 794 | Arlington - Velo Interlocken | Bld 3 Stair Core 1 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2024-10-28 | 2024-11-04 | 0.9 | All but WHR
900 | 795 | Arlington - Velo Interlocken | Bld 3 Stair Core 2 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2024-10-28 | 2024-11-04 | 0.9 | All but WHR
900 | 790 | Arlington - Velo Interlocken | Bld 1 Stair Core 1 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-06 | 0.9 | All but WHR
900 | 791 | Arlington - Velo Interlocken | Bld 1 Stair Core 2 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-06 | 0.9 | All but WHR
900 | 792 | Arlington - Velo Interlocken | Bld 2 Stair Core 1 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2024-10-07 | 2024-10-14 | 0.9 | All but WHR
900 | 793 | Arlington - Velo Interlocken | Bld 2 Stair Core 2 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2024-10-07 | 2024-10-14 | 0.9 | All but WHR
900 | 796 | Arlington - Velo Interlocken | Bld 4 Stair Core 1 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-06 | 0.9 | All but WHR
900 | 797 | Arlington - Velo Interlocken | Bld 4 Stair Core 2 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-06 | 0.9 | All but WHR
340 | 415 | AMLI - Littleton Village II | Structural Framing at Leasing Fireplace | 7.5 | 8.3 | Red Oxide Primed | DR | FMW | 2025-05-21 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-30 | O | QC Done
370 | 512 | Fairfield Development - Vista Highlands | Bld 15 Embeded posts | 0 | 3.1875 | Factory Black | GA | CBA | 2025-06-17 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-30 | O
370 | 521 | Fairfield Development - Vista Highlands | Bld 14 Embeded posts | 0 | 2.2031 | Factory Black | GA | CBA | 2025-06-17 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-30 | O
380 | 437 | Brinkman - Marshall Pointe | Garage Stair Core 1 Guard Rails | 40.825 | 38.825 | Red Oxide Primed | GA | CBA | 2025-05-29 | 1 | X | X | X | X | X | 2025-06-19 | 2025-06-23 | O
170 | 449 | Garrett -Banyan High Point | Building 4 Roof Screen Frame | 31.472 | 28 | Railing Black 38/81009 | RL | CBA | 2025-05-28 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-31 | O | QC Done
420 | 486 | Thompson Thrift - Stack at Wheat Ridge | Structural Steel Embeds | 0 | 0 | Raw Finish | DR | RJA | 2025-06-16 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-30 | O
380 | V793 | Brinkman - Marshall Pointe | (1) Column Baseplate | 0.5 | 2 | Red Oxide Primed | GA | GA | 2025-06-17 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-30 | O
200 | 436 | TCR - Alexan Diagonal | Bld 3 Patio Rails | 49 | 35 | Railing Black | DR | DCR | 2025-05-29 | 2 | X | X | X | X | T | 2025-07-30 | 2025-08-01 |  | QC Done
200 | 261 | TCR - Alexan Diagonal | Bldg 1 Garage Screen East | 47.5 | 47.5 | Railing Black | DR | SDO | 2025-02-27 | 2 | X | X | X | X | T | 2025-07-30 | 2025-08-01 |  | QC Done
320 | 371 | Thompson Thrift - Landing at Lemay | Building 2 Carraige house juliet | 0.5452 | 3.1726 | Factory Black | DR | CBA | 2025-04-29 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-30
320 | 331 | Thompson Thrift - Landing at Lemay | Building 3 Carraige house juliet | 0.5452 | 3.1726 | Factory Black | DR | CBA | 2025-04-15 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-30
320 | 404 | Thompson Thrift - Landing at Lemay | Bilding 6 Patio & Balcony Ultralox Rails P1 of 2 | 9.4564 | 110.0564 | Factory Balck | DR | CBA | 2025-05-02 | 2 | X | X | X | X | T | 2025-06-23 | 2025-07-01
320 | 398 | Thompson Thrift - Landing at Lemay | Building 5 Carraige house juliet | 0.5452 | 3.1726 | Factory Black | DR | CBA | 2025-05-02 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-30
320 | 397 | Thompson Thrift - Landing at Lemay | Building 4 Carraige house juliet | 0.5452 | 3.1726 | Factory Black | DR | CBA | 2025-05-02 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-30
320 | 352 | Thompson Thrift - Landing at Lemay | Building 1 Middle Stair | 22.5 | 21 | Railing Black | DR | CBA | 2025-04-15 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-31
320 | 344 | Thompson Thrift - Landing at Lemay | Building 1 West Stair | 22.5 | 21 | Railing Black | DR | CBA | 2025-04-01 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-31
320 | 353 | Thompson Thrift - Landing at Lemay | Building 1 East Stair | 22.5 | 21 | Railing Black | DR | CBA | 2025-04-15 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-31
320 | 399 | Thompson Thrift - Landing at Lemay | Building 6 East Stair | 22.5 | 21 | Railing Black | DR | CBA | 2025-05-06 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-31 |  | Powdered Waiting on 1 1/2 " SDS
340 | 409 | AMLI - Littleton Village II | Stair Core B Guard Rails | 48.099 | 43.599 | Red Oxide Primed | DR | CBA | 2025-05-09 | 2 | X | X | X | X | T | 2025-07-30 | 2025-08-01 |  | QC Done
340 | 423 | AMLI - Littleton Village II | Stair Core A Guard Rails | 65 | 59.25 | Red Oxide Primed | DR | CBA | 2025-05-22 | 2 | X | X | X | X | T | 2025-07-30 | 2025-08-04 |  | QC Done
130 | 338 | Fairfield - Arista Fairfield | Bld 9 CMU Retaining Wall Guardrail North | 13.3 | 2 | Red Oxide Primed | GA | DCR | 2025-04-22 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-30 |  | QC Done
130 | 426 | Fairfield - Arista Fairfield | Bldg 13 Roof Access Ladder | 3 | 3 | Red Oxide Primed | GA | CBA | 2025-05-28 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-30 |  | QC Done
190 | 245 | Hinton - Metro Center | Bld 1 Stoop Landing Guardrails | 17.5 | 17.5 | Railing Black | GA | DCR | 2025-02-05 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-31 |  | QC Done
190 | 390 | Hinton - Metro Center | Bld 3 Balcony Guardrail | 179.75 | 179.75 | Railing Black | GA | DCR | 2025-04-28 | 2 | X | X | X | X | T | 2025-07-30 | 2025-08-14 |  | QC Done
190 | 413 | Hinton - Metro Center | Bld 2 Balcony East | 91.25 | 91.25 | Railing Black | GA | DCR | 2025-05-21 | 2 | X | X | X | X | T | 2025-07-30 | 2025-08-06 |  | QC Done
190 | 442 | Hinton - Metro Center | Remaining Awning Clevis & Knife Plates | 10.5 | 0 | Red Oxide Primed | GA | DCR | 2025-05-29 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-30 |  | Clevis rods delivered 6/17
190 | 499 | Hinton - Metro Center | Bld 4 Sky Lounge Standoffs | 0 | 0 | RAW | GA | DCR | 2025-06-09 | 2 | X | X | X | X | T | 2025-06-17 | 2025-06-17 |  | Only need (5)
190 | 461 | Hinton - Metro Center | Bld 4 Roof Access Ladder | 3 | 3 | Red Oxide Primed | GA | DCR | 2025-06-02 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-30 |  | QC Done
300 | 771 | PCL - 16th Street Mall | Planter Railing | 213 | 142 | Custom RAL 6033 (Mint) | GA | SDO | 2024-07-29 | 2 | X | X | X | X | O | 2025-07-30 | 2025-08-11
380 | 376 | Brinkman - Marshall Pointe | Structural Columns & Beams Install Area C | 0 | 42.7375 | S.W. Epoxy Primer | GA | SDO | 2025-04-21 | 2 | X | X | X | X | T | 2025-07-30 | 2025-08-01
380 | 377 | Brinkman - Marshall Pointe | Structural Columns & Beams Install Area D | 0 | 37.2 | S.W. Epoxy Primer | GA | SDO | 2025-04-21 | 2 | X | X | X | X | O | 2025-07-30 | 2025-08-01
380 | 378 | Brinkman - Marshall Pointe | Structural Columns & Beams Install Area E | 0 | 14 | S.W. Epoxy Primer | GA | SDO | 2025-04-21 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
380 | 379 | Brinkman - Marshall Pointe | Structural Columns & Beams Install Area F | 0 | 45.8625 | S.W. Epoxy Primer | GA | SDO | 2025-04-21 | 2 | X | X | X | X | O | 2025-07-30 | 2025-08-01
380 | 382 | Brinkman - Marshall Pointe | Structural Columns & Beams Install Area J | 0 | 4 | S.W. Epoxy Primer | GA | SDO | 2025-04-21 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
380 | 383 | Brinkman - Marshall Pointe | Structural Columns & Beams Install Area K | 0 | 4 | S.W. Epoxy Primer | GA | SDO | 2025-04-21 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
170 | 492 | Garrett -Banyan High Point | Building 1 Roof Screen Frame | 66.316 | 59 | Railling Black 38/81009 | RL | CBA | 2025-06-09 | 2 | X | X | X | X | O | 2025-07-30 | 2025-08-04
170 | 493 | Garrett -Banyan High Point | Building 2 Roof Screen Frame | 66.316 | 59 | Railling Black 38/81009 | RL | CBA | 2025-06-09 | 2 | X | X | X | X | O | 2025-07-30 | 2025-08-04
170 | 494 | Garrett -Banyan High Point | Building 3 Roof Screen Frame | 31.472 | 28 | Railling Black 38/81009 | RL | CBA | 2025-06-09 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
170 | 496 | Garrett -Banyan High Point | Building 6 Roof Screen Frame | 31.472 | 28 | Railling Black 38/81009 | RL | CBA | 2025-06-09 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
170 | 495 | Garrett -Banyan High Point | Building 5 Roof Screen Frame | 18.265 | 16.25 | Railling Black 38/81009 | RL | CBA | 2025-06-09 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
330 | 443 | Brinkmann - Aspendale Littleton Senior | Roof Mechanical Screens Angles | 9.7125 | 97.125 | Red Oxide Primed | RL | CBA | 2025-05-27 | 2 | X | X | X | X | T | 2025-07-30 | 2025-08-07
330 | 447 | Brinkmann - Aspendale Littleton Senior | Roof Access Ladder | 5 | 4 | Railing Black | RL | DCR | 2025-05-27 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-30
440 | 478 | Evergreen - Outlook Green Valley Ranch | Bld 16 HD Embed Install | 0 | 15.05 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
440 | 477 | Evergreen - Outlook Green Valley Ranch | Bld 15 HD Embed Install | 0 | 17.5 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
440 | 476 | Evergreen - Outlook Green Valley Ranch | Bld 14 HD Embed Install | 0 | 7 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
440 | 475 | Evergreen - Outlook Green Valley Ranch | Bld 13 HD Embed Install | 0 | 7 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
440 | 472 | Evergreen - Outlook Green Valley Ranch | Bld 12 HD Embed Install | 0 | 15.05 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
440 | 471 | Evergreen - Outlook Green Valley Ranch | Bld 11 HD Embed Install | 0 | 21 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
440 | 470 | Evergreen - Outlook Green Valley Ranch | Bld 10 HD Embed Install | 0 | 15.05 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
440 | 469 | Evergreen - Outlook Green Valley Ranch | Bld 9 HD Embed Install | 0 | 17.5 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
440 | 468 | Evergreen - Outlook Green Valley Ranch | Bld 8 HD Embed Install | 0 | 17.5 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
440 | 467 | Evergreen - Outlook Green Valley Ranch | Bld 7 HD Embed Install | 0 | 17.5 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
440 | 466 | Evergreen - Outlook Green Valley Ranch | Bld 6 HD Embed Install | 0 | 17.5 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
440 | 465 | Evergreen - Outlook Green Valley Ranch | Bld 5 HD Embed Install | 0 | 17.5 | Raw | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
440 | 463 | Evergreen - Outlook Green Valley Ranch | Bld 4 HD Embed Install | 0 | 7 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
440 | 460 | Evergreen - Outlook Green Valley Ranch | Bld 3 HD Embed Install | 0 | 7 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
440 | 464 | Evergreen - Outlook Green Valley Ranch | Bld 2 HD Embed Install | 0 | 17.5 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
440 | 462 | Evergreen - Outlook Green Valley Ranch | Bld 1 HD Embed Install | 0 | 6.3 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
900 | 250 | Arlington - Velo Interlocken | Bld 5 Balconies | 147.087 | 122.5 | Railing Black | RL | DCR | 2025-02-10 | 2 | X | X | X | X | T | 2025-07-30 | 2025-08-08 |  | Wait to ship
370 | 474 | Fairfield Development - Vista Highlands | Roof Access Ladder Type A Bld 4 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
370 | 497 | Fairfield Development - Vista Highlands | Roof Access Ladder Type A Bld 6 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
370 | 498 | Fairfield Development - Vista Highlands | Roof Access Ladder Type A Bld 7 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
370 | 500 | Fairfield Development - Vista Highlands | Roof Access Ladder Type A Bld 8 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
370 | 501 | Fairfield Development - Vista Highlands | Roof Access Ladder Type A Bld 9 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
370 | 502 | Fairfield Development - Vista Highlands | Roof Access Ladder Type A Bld 11 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
370 | 503 | Fairfield Development - Vista Highlands | Roof Access Ladder Type A Bld 14 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
370 | 504 | Fairfield Development - Vista Highlands | Roof Access Ladder Type B Bld 2 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
370 | 505 | Fairfield Development - Vista Highlands | Roof Access Ladder Type B Bld 3 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
370 | 506 | Fairfield Development - Vista Highlands | Roof Access Ladder Type B Bld 5 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
370 | 523 | Fairfield Development - Vista Highlands | Bld 13 Embeded posts | 0 | 2.9375 | Factory Black | GA | CBA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
370 | 525 | Fairfield Development - Vista Highlands | Bld 2 Embeded posts | 0 | 2.9375 | Factory Black | GA | CBA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
370 | 530 | Fairfield Development - Vista Highlands | Bld 4 Embeded posts | 0 | 2.2031 | Factory Black | GA | CBA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
370 | 527 | Fairfield Development - Vista Highlands | Bld 3 Embeded posts | 0 | 2.9375 | Factory Black | GA | CBA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
370 | 507 | Fairfield Development - Vista Highlands | Roof Access Ladder Type B Bld 12 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
370 | 508 | Fairfield Development - Vista Highlands | Roof Access Ladder Type B Bld 13 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
370 | 509 | Fairfield Development - Vista Highlands | Roof Access Ladder Type C Bld 10 | 0 | 9 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
370 | 510 | Fairfield Development - Vista Highlands | Roof Access Ladder Type C Bld 15 | 0 | 9 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
170 | 183 | Garrett -Banyan High Point | Entrance Canopies | 143 | 256 | Red Oxide Primed | RL | CBA | 2025-01-08 | 4 | X | X | X | X | X | 2025-07-30 | 2025-08-21 | O | WORKING
900 | 276 | Arlington - Velo Interlocken | Bld 6 Balconies | 147.087 | 122.5 | Railing Black | RL | DCR | 2025-02-27 | 5 | X | X | X | O | T | 2025-07-30 | 2025-08-08 |  | QC Done
190 | 248 | Hinton - Metro Center | Bld 2 Stoop Landing Guardrails | 70 | 70 | Railing Black | GA | DCR | 2025-02-28 | 6 | X | X | X | O | T | 2025-07-30 | 2025-08-05 |  | QC Done
900 | V862 | Arlington - Velo Interlocken | Bottom Saddle Clips | 3.5 | 1 | Railing Black | RL | RL | 2025-04-15 | 7 | X | X | X | O |  | 2025-07-30 | 2025-07-30 |  | 50 are done
320 | 401 | Thompson Thrift - Landing at Lemay | Building 6 West Stair | 22.5 | 21 | Railing Black 38/81009 | DR | CBA | 2025-05-02 | 8 | X | X | X | O | T | 2025-07-30 | 2025-07-31 |  | Rework done
320 | 400 | Thompson Thrift - Landing at Lemay | Building 6 Middle Stair | 22.5 | 21 | Railing Black 38/81009 | DR | CBA | 2025-05-07 | 9 | X | X | X | O | T | 2025-07-30 | 2025-07-31 |  | Rework done
380 | 414 | Brinkman - Marshall Pointe | Roof Screens | 147 | 392 | Raven Black | GA | RJA | 2025-05-15 | 10 | X | X | X | O | T | 2025-07-30 | 2025-09-02 |  | test mpte jaaaas
330 | 430 | Brinkmann - Aspendale Littleton | Roof Mechanical Screens posts | 146.8125 | 195.75 | Red Oxide Primed | RL | CBA | 2025-05-23 | 11 | X | X | O |  |  | 2025-07-31 | 2025-08-18 |  | test note
380 | 485 | Brinkman - Marshall Pointe | Structural Columns & Beams Leave Out Area A | 174.4598 | 116.4792 | 1 HR. intumescent | GA | CBA | 2025-06-04 | 12 | X | X | X | O | T | 2025-06-19 | 2025-06-30 |  | QC Done
340 | 421 | AMLI - Littleton Village II | Structural Steel | 1050.5498 | 694.9416 | Primmed and Iutumescent | DR | DTS | 2025-05-27 | 13 | X | X | O |  |  | 2025-07-10 | 2025-09-09 |  | plates are here
260 | 347 | Hinton - Kairoi (Tripoint) | WWM Screen Entrance Gates | 23.5 | 17 | BK247 | GA | DCR | 2025-04-03 | 14 | X | X | O |  | T | 2025-08-07 | 2025-08-08 |  | BK247 (off hold CO executed) mesh is here
190 | 168 | Hinton - Metro Center | Bld 4 Ramp Rail | 23.5 | 22 | Railing Black | GA | DCR | 2025-06-03 | 15 | X | X | O |  | T | 2025-08-07 | 2025-08-08
260 | 483 | Hinton - Kairoi (Tripoint) | Garage Fence | 115 | 98 | BK 247 | GA | DCR | 2025-06-03 | 16 | X | x | O |  |  | 2025-08-08 | 2025-08-18
370 | 455 | Fairfield Development - Vista Highlands | Bld 15 Stair 1 Rails | 11.25 | 9 | TBD | GA | DCR | 2025-06-02 | 17 | X | X | X | O | T | 2025-08-08 | 2025-08-08 |  | QC Done
370 | 458 | Fairfield Development - Vista Highlands | Bld 15 Stair 2 Rails | 11.25 | 9 | TBD | GA | DCR | 2025-06-02 | 18 | X | X | O |  |  | 2025-08-08 | 2025-08-08
370 | 459 | Fairfield Development - Vista Highlands | Bld 15 Stair 3 Rails | 11.25 | 9 | TBD | GA | DCR | 2025-06-02 | 19 | X | X | O |  |  | 2025-08-08 | 2025-08-08
380 | 444 | Brinkman - Marshall Pointe | Garage Stair Core 3 Guard Rails | 57 | 52.75 | Red Oxide Primed | GA | CBA | 2025-06-04 | 20 | X | X | HOLD |  |  | 2025-06-25 | 2025-06-30 |  | HOLD
200 | V326 | TCR - Alexan Diagonal | Replacement Angles for Bike storage Fence |  |  | Railing Black 38/81009 | DR | DR | 2025-06-11 | 21 | X | O |  |  |  | 2025-06-17 | 2025-06-17 |  | HOT NEED ASAP. Waiting on new punch. Due 6/18
160 | 515 | Brinkmann - Wind Crest RB3.5 | Site Rails | 24.7843 | 20.9718 | Statuary Bronze | DR | DCR | 2025-06-13 | 22 | X | O |  |  |  | 2025-06-24 | 2025-06-25
475 | 536 | Macy Development - Bristol Pointe Apt. | Stair Tread Repair | 1.38 | 0 | Cardinal BR-23 | WO | DTS | 2025-06-18 | 23 | HOT |  |  |  |  | 2025-06-25 | 2025-06-25
170 | 451 | Garrett -Banyan High Point | Trellis B | 45.6 | 46.6 | Red Oxide Primed | RL | FMW | 2025-06-03 | 40 | O |  |  |  |  | 2025-08-11 | 2025-08-13 |  | Need embeds done.
170 | 457 | Garrett -Banyan High Point | Pool Courtyard Trellis | 67.5 | 68.5 | Red Oxide Primed | RL | FMW | 2025-06-03 | 41 | O |  |  |  |  | 2025-08-12 | 2025-08-18 |  | Need embeds done.
370 | 479 | Fairfield Development - Vista Highlands | Bld 14 Stair 1 Rails | 11.25 | 9 | Railing Black | GA | DCR | 2025-06-05 | 25 | X | O |  |  |  | 2025-08-12 | 2025-08-12
370 | 480 | Fairfield Development - Vista Highlands | Bld 14 Stair 2 Rails | 11.25 | 9 | Railing Black | GA | DCR | 2025-06-05 | 26 | X | O |  |  |  | 2025-08-12 | 2025-08-12
380 | 487 | Brinkman - Marshall Pointe | CMU Angles | 16.64 | 33.28 | Red Oxide Primed | GA | CBA | 2025-06-09 | 27 | O |  |  |  | T | 2025-08-12 | 2025-08-14 |  | HOT
260 | 412 | Hinton - Kairoi (Tripoint) | Garage Door Steel Frame Center | 10 | 10 | BK247 | GA | DTS | 2025-06-10 | 80 | O |  |  |  |  | 2025-06-26 | 2025-06-26 |  | STOP, SCOPE PULLED
260 | 110 | Hinton - Kairoi (Tripoint) | Dog Park Fence | 45.5 | 91 | TBD | GA | DCR | 2025-06-10 | 28 | X | O |  |  |  | 2025-08-13 | 2025-08-20 |  | perf is here
260 | 511 | Hinton - Kairoi (Tripoint) | Center Garage Fence | 81.5 | 69 | BK 247 | GA | DCR | 2025-06-12 | 29 | O |  |  |  |  | 2025-08-13 | 2025-08-19
200 | 516 | TCR - Alexan Diagonal | Elevator Sump Pit Cover | 8 | 8 | Red Ox | DR | DCR | 2025-06-11 | 12.5 | X | X | X | O | T | 2025-08-13 | 2025-08-13
900 | 517 | Arlington - Velo Interlocken | Maintenance Shed Rail | 2.5 | 1 | Railing Black | RL | DCR | 2025-06-12 | 34 | O |  |  |  |  | 2025-08-13 | 2025-08-13
140 | 518 | 140 ASR - Crestview | Sleek Fence Privacy Screens Phase 2 | 0.9 | 18 | Sleek Black | WO | DCR | 2025-06-13 | 33 | - |  |  |  |  | 2025-08-13 | 2025-08-14
370 | 534 | Fairfield Development - Vista Highlands | Bulk Roof Ladder Pack | 90 | 0 | Railing Black | GA | RJA | 2025-06-17 | 32 | O |  |  |  |  | 2025-08-14 | 2025-08-14
460 | 489 | Mountain West Contractors - Dublin Springs | Balcony Rails | 245.9312 | 281 | Railing Black | GA | DCR | 2025-06-18 | 31 | HOT |  |  |  |  | 2025-07-03 | 2025-07-28
340 | 456 | AMLI - Littleton Village II | Structural Intumescent Paint | 0 | 174.7 | Intumescent Paint | DR | DTS | 2025-05-29 | 80.555 | - |  |  |  |  | 2025-08-19 | 2025-09-02
170 | 520 | Garrett -Banyan High Point | Bld 4 Balcony Rails | 132.7736 | 118 | Railing Black | RL | DCR | 2025-06-18 | 80.555 | - |  |  |  |  | 2025-08-20 | 2025-08-29
900 | 540 | Arlington - Velo Interlocken | Bld 1 4th Floor Corner Balconies | 10 | 8.5 | Railing Black | RL | DCR | 2025-06-18 | 80.555 | - |  |  |  |  | 2025-08-20 | 2025-08-20
170 | 285 | Garrett -Banyan High Point | Building 1 Canopy | 0 | 13.3333 | Red Oxide Primed | RL | CBA | 2025-06-19 | 80.555 | X | X | X | X | O | 2025-08-20 | 2025-08-20
170 | 284 | Garrett -Banyan High Point | Building 1 Canopy Plates | 0 | 26.6667 | Red Oxide Primed | RL | CBA | 2025-06-19 | 80.555 | X | X | X | X | O | 2025-08-20 | 2025-08-21
170 | 287 | Garrett -Banyan High Point | Building 2 Canopy | 0 | 8 | Red Oxide Primed | RL | CBA | 2025-06-19 | 80.555 | X | X | X | X | O | 2025-08-20 | 2025-08-20
170 | 286 | Garrett -Banyan High Point | Building 2 Canopy Plates | 0 | 16 | Red Oxide Primed | RL | CBA | 2025-06-19 | 80.555 | X | X | X | X | O | 2025-08-20 | 2025-08-21
170 | 289 | Garrett -Banyan High Point | Building 3 Canopy | 0 | 16 | Red Oxide Primed | RL | CBA | 2025-06-19 | 80.555 | X | X | X | X | O | 2025-08-20 | 2025-08-21
170 | 288 | Garrett -Banyan High Point | Building 3 Canopy Plates | 0 | 32 | Red Oxide Primed | RL | CBA | 2025-06-19 | 80.555 | X | X | X | X | O | 2025-08-20 | 2025-08-22
170 | 293 | Garrett -Banyan High Point | Building 5 Canopy | 0 | 16 | Red Oxide Primed | RL | CBA | 2025-06-19 | 80.555 | X | X | X | X | O | 2025-08-20 | 2025-08-21
170 | 292 | Garrett -Banyan High Point | Building 5 Canopy Plates | 0 | 32 | Red Oxide Primed | RL | CBA | 2025-06-19 | 80.555 | X | X | X | X | O | 2025-08-20 | 2025-08-22
170 | 295 | Garrett -Banyan High Point | Building 6 Canopy | 0 | 16 | Red Oxide Primed | RL | CBA | 2025-06-19 | 80.555 | X | X | X | X | O | 2025-08-20 | 2025-08-21
170 | 294 | Garrett -Banyan High Point | Building 6 Canopy Plates | 0 | 32 | Red Oxide Primed | RL | CBA | 2025-06-19 | 80.555 | X | X | X | X | O | 2025-08-20 | 2025-08-22
190 | 535 | Hinton - Metro Center | Bld 3 Stair & Ramp Rails North | 12.5 | 10 | Red Oxide Primed | GA | DCR | 2025-06-19 | 80.555 | - |  |  |  |  | 2025-08-20 | 2025-08-20
190 | 538 | Hinton - Metro Center | Bld 3 Stair & Ramp Rails South | 17.5 | 14 | Red Oxide Primed | GA | DCR | 2025-06-19 | 80.555 | - |  |  |  |  | 2025-08-20 | 2025-08-20
[10 empty] | 80.555 | - |  |  |  |  | 2025-08-20
[10 empty] | 80.555 | - |  |  |  |  | 2025-08-20
[10 empty] | 80.555 | - |  |  |  |  | 2025-08-20
[10 empty] | 80.555 | - |  |  |  |  | 2025-08-20