## Submittals
Submittals Id | Project Name | Title | Ball In Court Due Date | Final Due Date | Status | Type | Ball In Court | Response | Submittal Manager
64452445 | Misc. Project MHMW | Wyobraska Vet sign | 2025-07-27 | 2025-08-01 | Open | Submittal For Gc Approval | Bill O'Neill | Approved, Revise and Resubmit, For Record Only, Approved, Approved, Pending, Pending | Bill O'Neill
65206107 | Misc. Project MHMW | MHMW new location | 2025-11-09 | 2025-11-19 | Open | Submittal For Gc Approval | Bill O'Neill | Revise and Resubmit, Revise and Resubmit, For Record Only, Approved, Approved, For Record Only, Approved as Noted, Approved, Approved, For Record Only, Revise and Resubmit, Pending, Pending, Pending | Bill O'Neill
57913056 | Littleton Village II | Add Alternate Unit Budget - Countertop Support Brackets | 2025-02-24 | 2025-03-01 | Open | Submittal For Gc Approval | Danny Riddell | Approved, Approved as Noted, Pending, Pending | Danny Riddell
57913057 | Littleton Village II | Add Alternate - Bike Racks | 2025-01-20 | 2025-01-20 | Open | Submittal For Gc Approval | Danny Riddell | Approved, Approved, Approved, Pending | Danny Riddell
63012208 | Littleton Village II | Drink Ledge at Pool Courtyard | 2025-05-10 | 2025-05-20 | Open | Submittal For Gc Approval | Danny Riddell | Approved, For Record Only, Pending, Pending, Pending, Pending | Danny Riddell
63408742 | Littleton Village II | Garage Parapet & OSHA Railing | 2025-05-25 | 2025-06-14 | Open | Drafting Release Review | Danny Riddell | Forwarded For Review, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
65338470 | Sandstone Ranch | Roof Hatch Access Ladder and Security Gate |  | 2025-08-24 | Open | Submittal For Gc Approval | Danny Riddell | For Record Only, Revise and Resubmit, Revise and Resubmit, For Record Only, Approved | Danny Riddell
66445526 | 530- East Oak Townhomes | Stair Stringers @ Level 2 to Level 3 at Each Unit | 2025-10-28 | 2025-12-07 | Open | Submittal For Gc Approval | Danny Riddell | Approved, Revise and Resubmit, Pending, Approved, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
66445558 | 530- East Oak Townhomes | Balcony Guardrails | 2025-10-26 | 2025-12-05 | Open | Submittal For Gc Approval | Danny Riddell | Approved, Approved, Revise and Resubmit, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
66445651 | 530- East Oak Townhomes | Steel Handrail @ Level 4 Parapet | 2025-10-15 | 2025-11-04 | Open | Submittal For Gc Approval | Danny Riddell | For Record Only, Revise and Resubmit, Pending, Revise and Resubmit, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
66445719 | 530- East Oak Townhomes | Unit type A/C porch handrail | 2025-10-11 | 2025-10-31 | Open | Submittal For Gc Approval | Danny Riddell | For Record Only, Pending, Approved as Noted, Revise and Resubmit, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
66445736 | 530- East Oak Townhomes | Roof Access Ladder and Gate | 2025-11-09 | 2025-12-19 | Open | Submittal For Gc Approval | Danny Riddell | Approved, Revise and Resubmit, Revise and Resubmit, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
66445770 | 530- East Oak Townhomes | Bay Window Steel Framing | 2025-10-22 | 2025-12-01 | Open | Submittal For Gc Approval | Danny Riddell | Approved, Approved, Approved as Noted, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
66838267 | Sandstone Ranch | Low Metal Canopy at 2nd levels only | 2025-10-22 | 2025-11-21 | Open | Submittal For Gc Approval | Danny Riddell | Approved, Revise and Resubmit, Revise and Resubmit, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
66838594 | Sandstone Ranch | High Metal Canopy with slat infill | 2025-10-22 | 2025-11-21 | Open | Submittal For Gc Approval | Danny Riddell | Approved, Pending, Approved, Revise and Resubmit, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
61724059 | Marshall Pointe | Ramp Railings | 2025-11-12 | 2025-11-17 | Open | Drafting Release Review | Brian Panning | Approved as Noted, Approved, Revise and Resubmit, For Record Only, For Record Only, For Record Only, Revise and Resubmit, For Record Only, Approved, Pending, Pending | Gary Almeida
65884436 | Capital Hill | Stair Cores | 2025-11-04 | 2025-11-09 | Open | Submittal For Gc Approval | Brian Panning | Approved as Noted, Approved, Approved, Approved, Approved, Revise and Resubmit, Approved, For Record Only, Pending, Pending | Gary Almeida
65112006 | Novel Flatiron Crossing | Garage Entry Steel | 2025-11-10 | 2025-11-15 | Open | Submittal For Gc Approval | David Servold | For Record Only, Approved, For Record Only, Approved as Noted, Pending, Pending | Gary Almeida
65112007 | Novel Flatiron Crossing | Amenity Steel | 2025-08-05 | 2025-08-15 | Open | Submittal For Gc Approval | David Servold | Pending, Pending, Pending | Gary Almeida
66109564 | Columbine Square | Building 4 Structural Steel Package | 2025-10-11 | 2025-10-21 | Open | Drafting Release Review | David Servold | For Record Only, Approved as Noted, Approved as Noted, Pending, Pending, Pending, Pending | Rich Losasso
66109641 | Columbine Square | Building 4 Structural Embed Package | 2025-10-11 | 2025-10-21 | Open | Drafting Release Review | David Servold | For Record Only, Pending, Approved as Noted, Approved, Pending, Pending, Pending | Rich Losasso
66156110 | Columbine Square | Building 6 Structural Embed Package | 2025-11-08 | 2025-11-13 | Open | Drafting Release Review | David Servold | For Record Only, Approved as Noted, Revise and Resubmit, Approved, For Record Only, Pending, Approved, Pending | Rich Losasso
66676595 | 530- East Oak Townhomes | Sun Shade Structure | 2025-11-11 | 2025-12-01 | Open | Submittal For Gc Approval | David Servold | For Record Only, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
67124398 | Novel Flatiron Crossing | Site embeds | 2025-11-02 | 2025-11-17 | Open | Submittal For Gc Approval | David Servold | Pending, Forwarded For Review, Rejected, Pending, Pending, Pending, Pending, Pending | Gary Almeida
67308034 | Martin Residence | Interior guard rail | 2025-11-10 | 2025-11-15 | Open | Submittal For Gc Approval | David Servold | Pending, Pending, Pending | Gary Almeida
60714842 | Heritage on Hover | Stair Rails | 2025-11-08 | 2025-11-23 | Open | Submittal For Gc Approval | Colton Arendt | Approved, Revise and Resubmit, For Record Only, Approved, Revise and Resubmit, Pending, Pending, Pending, Pending | Rich Losasso
61749099 | Martin Residence | Interior Stair | 2025-03-18 | 2025-04-02 | Open | Submittal For Gc Approval | Colton Arendt | Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
65961346 | Aspendale Littleton (Headwaters) | Covered Walkway | 2025-11-15 | 2025-11-20 | Open | Submittal For Gc Approval | Colton Arendt | Approved, Revise and Resubmit, Approved, Approved, Revise and Resubmit, For Record Only, Pending, Pending, Pending | Rich Losasso
65961512 | Aspendale Littleton (Headwaters) | Courtyard Trellis (Ownership) | 2025-11-08 | 2025-11-18 | Open | Submittal For Gc Approval | Colton Arendt | Revise and Resubmit, Approved, Revise and Resubmit, Pending, Pending, Pending | Rich Losasso
66445618 | 530- East Oak Townhomes | Level 1 Patio Privacy Screen | 2025-10-07 | 2025-11-21 | Open | Submittal For Gc Approval | Colton Arendt | Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
66854819 | Marshall Pointe | NorthEast Exterior Balconies | 2025-10-20 | 2025-10-30 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Gary Almeida
66854834 | Marshall Pointe | NorthWest Exterior Balconies | 2025-10-20 | 2025-10-30 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Gary Almeida
66927442 | Metro Center | CO#23 - Sidewalk Chase Covers | 2025-11-02 | 2025-11-07 | Open | Submittal For Gc Approval | Colton Arendt | Approved, Revise and Resubmit, Revise and Resubmit, For Record Only, Revise and Resubmit, Pending, Pending, Pending | Gary Almeida
67123356 | Velo Interlocken | Drainage Rails ( EZ Excavating) | 2025-11-02 | 2025-11-17 | Open | Submittal For Gc Approval | Colton Arendt | Pending, Pending, Pending, Pending, Pending, Pending | Rich Losasso
67152419 | Novel Flatiron Crossing | Non-Bearing CMU Partition Bracing Embeds and Angles | 2025-11-03 | 2025-11-13 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending, Pending | Gary Almeida
67184837 | Marshall Pointe | MHMW CO#17 - Garage Low Wall Railing | 2025-11-04 | 2025-11-19 | Open | Submittal For Gc Approval | Colton Arendt | Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
67249416 | Aspendale Littleton (Headwaters) | Covered Walkway Steel | 2025-11-08 | 2025-11-23 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67269119 | Vista Highlands | Bld 9 Balconies | 2025-11-09 | 2025-11-19 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending, Pending | Gary Almeida
67269128 | Vista Highlands | Bld 10 Balconies | 2025-11-09 | 2025-11-19 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending, Pending | Gary Almeida
67269134 | Vista Highlands | Bld 11 Balconies | 2025-11-09 | 2025-11-19 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending, Pending | Gary Almeida
67269153 | Vista Highlands | Bld 12 Balconies | 2025-11-09 | 2025-11-19 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending, Pending | Gary Almeida
67300445 | Misc. Project MHMW | Compactor Shading | 2025-11-10 | 2025-11-25 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67303541 | Columbine Square | Building 2 stair core 1 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67303582 | Columbine Square | Building 2 stair core 2 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67303661 | Columbine Square | Building 2 stair core 3 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67303715 | Columbine Square | Building 4 stair core 1 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67303825 | Columbine Square | Building 4 stair core 2 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67303926 | Columbine Square | Building 5 stair core 1 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67303960 | Columbine Square | Building 5 stair core 2 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67304001 | Columbine Square | Building 5 stair core 3 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67304038 | Columbine Square | Building 6 stair core 1 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67304068 | Columbine Square | Building 6 stair core 2 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67304230 | Columbine Square | Building 7 stair core 1 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67304303 | Columbine Square | Building 7 stair core 2 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67304570 | Columbine Square | Building 7 stair core 3 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67336301 | Sandstone Ranch | Fitness Stair | 2025-11-11 | 2025-12-01 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
67336370 | 320 Landing at Lemay | Building #16 South Stair | 2025-11-11 | 2025-12-01 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
67336442 | 320 Landing at Lemay | Building #16 North Stair | 2025-11-11 | 2025-12-01 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
67336553 | 320 Landing at Lemay | Building #16 Balcony and Patio Rails | 2025-11-11 | 2025-12-01 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
63956243 | Alta Flatirons | ADD/ALT Open Space Shade Structure | 2025-07-01 | 2025-08-10 | Open | Submittal For Gc Approval | Gary Almeida | For Record Only, Pending, Revise and Resubmit, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
63956244 | Alta Flatirons | ADD/ALT Standard Bike Rack | 2025-06-26 | 2025-08-08 | Open | Submittal For Gc Approval | Gary Almeida | Forwarded For Review, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
64744482 | Olde Course Maintenance Building | Stair to Mezzanine | 2025-11-08 | 2025-11-23 | Open | Drafting Release Review | Gary Almeida | For Record Only, Approved, Revise and Resubmit, For Record Only, Approved, For Record Only, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
64951508 | Martin Residence | Front Entry Trellis Steel Framing | 2025-07-29 | 2025-08-08 | Open | Drafting Release Review | Gary Almeida | Pending, Forwarded For Review, Pending, Pending, Pending | Gary Almeida
65112024 | Novel Flatiron Crossing | Loose Lintels | 2025-11-11 | 2025-12-26 | Open | Submittal For Gc Approval | Gary Almeida | For Record Only, For Record Only, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
66212434 | Vista Highlands | CO#03 - Trellis A | 2025-09-24 | 2025-10-19 | Open | Drafting Release Review | Gary Almeida | Pending, Forwarded For Review, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
66992266 | Alta Flatirons | Site Guardrail | 2025-11-11 | 2025-11-26 | Open | Submittal For Gc Approval | Gary Almeida | Approved, Approved, Pending, Pending, Pending, Pending, Pending | Gary Almeida
66110509 | Heritage on Hover | Building A West Core | 2025-09-20 | 2025-10-05 | Open | Drafting Release Review | Rich Losasso | Pending, Forwarded For Review, Pending, Pending, Pending, Pending, Pending, Pending | Rich Losasso
66110537 | Heritage on Hover | Building A East Core | 2025-09-20 | 2025-10-05 | Open | Drafting Release Review | Rich Losasso | Pending, Forwarded For Review, Pending, Pending, Pending, Pending, Pending, Pending | Rich Losasso
66183685 | Aspendale Littleton (Headwaters) | Mockup Balcony Divider | 2025-09-30 | 2025-10-10 | Open | Drafting Release Review | Rich Losasso | Approved, Pending, Pending, Pending | Rich Losasso
66788316 | Outlook Green Valley Ranch | Building 2 Balcony Rail Install | 2025-11-12 | 2025-11-22 | Open | Drafting Release Review | Rich Losasso | Approved, Pending, Pending, Pending | Rich Losasso
66788515 | Outlook Green Valley Ranch | Building 5 Balcony Rail Install | 2025-11-11 | 2025-11-21 | Open | Drafting Release Review | Rich Losasso | Approved, Pending, Pending, Pending | Rich Losasso
66885801 | Idaho Springs Police Station | Eastside Structural Steel | 2025-11-08 | 2025-11-08 | Open | Submittal For Gc Approval | Rich Losasso | Approved, Revise and Resubmit, Approved, Pending | Rich Losasso
66885964 | Idaho Springs Police Station | Westside Structural Steel | 2025-11-12 | 2025-11-22 | Open | Submittal For Gc Approval | Rich Losasso | Approved, Revise and Resubmit, For Record Only, For Record Only, Pending, Pending, Pending | Rich Losasso
66997770 | Banyan High Point | Building 4 Exterior Stair Rail | 2025-11-10 | 2025-11-20 | Open | Drafting Release Review | Rich Losasso | Approved, Pending, Pending, Pending | Rich Losasso
67302402 | Columbine Square | Building 1 stair core 1 | 2025-11-08 | 2025-11-11 | Open | Drafting Release Review | Rich Losasso | Submitted, Pending, Pending, Pending | Rich Losasso
67302664 | Columbine Square | Building 1 stair core 2 | 2025-11-08 | 2025-11-11 | Open | Drafting Release Review | Rich Losasso | Approved, Pending, Pending, Pending | Rich Losasso
67302951 | Columbine Square | Building 1 stair core 3 | 2025-11-08 | 2025-11-11 | Open | Drafting Release Review | Rich Losasso | Approved, Pending, Pending, Pending | Rich Losasso
63325703 | Vista Highlands | bld 2 stair | 2025-05-21 | 2025-05-31 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending, Pending, Pending | Gary Almeida
65111996 | Novel Flatiron Crossing | Stair Cores #01 | 2025-08-31 | 2025-10-09 | Open | Submittal For Gc Approval | Dalton Rauer | Approved, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
65111997 | Novel Flatiron Crossing | Stair Core #02 | 2025-08-31 | 2025-10-09 | Open | Submittal For Gc Approval | Dalton Rauer | Approved, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
65112011 | Novel Flatiron Crossing | Stair #02 Vestibule Canopy | 2025-08-13 | 2025-09-21 | Open | Submittal For Gc Approval | Dalton Rauer | For Record Only, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
65619027 | Vista Highlands | Bld 6 Stair | 2025-08-27 | 2025-09-06 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending | Gary Almeida
65836286 | Novel Flatiron Crossing | Brick Relief Angle | 2025-09-21 | 2025-09-26 | Open | Submittal For Gc Approval | Dalton Rauer | Pending, For Record Only, Pending, Pending | Gary Almeida
65903588 | Metro Center | CO #21 Pool Fence | 2025-11-12 | 2025-11-17 | Open | Submittal For Gc Approval | Dalton Rauer | Approved, Approved as Noted, Approved, Approved, For Record Only, Approved, Revise and Resubmit, Pending, Pending | Gary Almeida
66088021 | Metro Center | Bld 5 Balconies | 2025-09-20 | 2025-09-30 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending, Pending | Gary Almeida
66196163 | Vista Highlands | Bld 8 Stairs | 2025-09-23 | 2025-10-03 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending | Gary Almeida
66196168 | Vista Highlands | Bld 7 Stairs | 2025-09-23 | 2025-10-03 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending | Gary Almeida
66198859 | Metro Center | Bld 5 Roof access Ladder | 2025-09-23 | 2025-10-03 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending | Gary Almeida
66791943 | Banyan High Point | Building 6 Balcony Rails | 2025-10-18 | 2025-11-02 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending, Pending | Rich Losasso
67118337 | Littleton Village II | Hanging Brick Relief at Storefront | 2025-11-12 | 2025-12-02 | Open | Drafting Release Review | Dalton Rauer | Approved, Approved as Noted, Approved as Noted, Revise and Resubmit, Pending, Pending, Pending, Pending, Pending | Danny Riddell
67269208 | Vista Highlands | Bld 9 Stair WHG | 2025-11-09 | 2025-11-19 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending, Pending, Pending | Gary Almeida
67269216 | Vista Highlands | Bld 10 Stair WHG | 2025-11-09 | 2025-11-19 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending, Pending, Pending | Gary Almeida
67269224 | Vista Highlands | Bld 11 Stair WHG | 2025-11-09 | 2025-11-19 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending, Pending, Pending | Gary Almeida
67269231 | Vista Highlands | Bld 12 Stair WHG | 2025-11-09 | 2025-11-19 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending, Pending, Pending | Gary Almeida
67336086 | Metro Center | Bld 2 interior Ramps | 2025-11-11 | 2025-11-21 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending, Pending | Gary Almeida
67336093 | Sandstone Ranch | Retaining Wall West Elevation | 2025-11-11 | 2025-12-01 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
67400030 | Littleton Village II | Commercial Awnings | 2025-11-15 | 2025-12-05 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
63956218 | Alta Flatirons | Structural Steel Beams | 2025-06-30 | 2025-07-05 | Open | Submittal For Gc Approval | Dominic Wenk | Pending, Pending, Pending | Gary Almeida
66685313 | Alta Flatirons | Structural Steel Columns Embeds | 2025-10-13 | 2025-11-27 | Open | Submittal For Gc Approval | Dominic Wenk | Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
60670523 | Marshall Pointe | Garage Pipe Protections | 2025-11-09 | 2025-11-19 | Open | Drafting Release Review | Rourke Alvarado | For Record Only, Pending, Pending, Pending, Pending | Gary Almeida
61723622 | Marshall Pointe | Garage Ramp Railings | 2025-08-26 | 2025-09-15 | Open | Drafting Release Review | Rourke Alvarado | Approved as Noted, Approved, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
65112004 | Novel Flatiron Crossing | Misc Railing & Handrails | 2025-11-08 | 2025-12-03 | Open | Submittal For Gc Approval | Rourke Alvarado | For Record Only, Approved, Revise and Resubmit, For Record Only, For Record Only, For Record Only, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
66156160 | Columbine Square | Building 6 Structural Steel Package | 2025-11-01 | 2025-11-06 | Open | Drafting Release Review | Rourke Alvarado | For Record Only, Approved as Noted, Approved as Noted, Approved, Pending, Pending, Pending | Rich Losasso
67138506 | Vista Highlands | Bld 14 Trash Enclosure Gates | 2025-11-02 | 2025-11-12 | Open | Drafting Release Review | Rourke Alvarado | Pending, Pending, Pending, Pending | Gary Almeida
67257375 | Columbine Square | Trash Enclosure Bollards Only | 2025-11-08 | 2025-11-23 | Open | Drafting Release Review | Dustin Pauley | Pending, Pending, Pending, Pending | Rich Losasso