## Sheet1
Job | Description | Fab Hrs | Install HRS | Paint color | PM | BY | Released | Fab Order | Cut start | Fitup comp | Welded | Paint Comp | Ship | Start install | Comp. ETA | Job Comp | Notes
TCR - Alexan Diagonal | Bldg 3 Stair 2 | 81.2684 | 123.9125 | Red Oxide Primed | DR | CBA | 2024-10-18 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-08 | 0.9 | All but WHR
Thompson Thrift - Landing at Lemay | Bilding 1 Patio & Balcony Ultralox Rails P1 of 2 | 9.1556 | 106.5556 | Factory Black | DR | CBA | 2025-04-23 | 1 | X | X | X | X | X | 2025-06-10 | 2025-06-18 | 0.5
AMLI - Littleton Village II | Garage Bollards | 18 | 18 | Safety Yellow | DR | DCR | 2025-05-14 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-31 | O | QC Done
Fairfield - Arista Fairfield | Bld 8 Balcony Rails | 84.9786 | 60.25 | Railing Black | GA | DCR | 2025-02-26 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-04 | 0.9 | QC Done
Fairfield - Arista Fairfield | Typ Awning | 516 | 516 | Railing Black | GA | DCR | 2024-01-18 | 1 | X | X | X | X | X | 2025-07-30 | 2025-09-12 | 0.8 | Bld 14, 1-11 complete Clubhouse
Fairfield - Arista Fairfield | Steel Canopies | 610.5 | 697.5 | Red-ox prime | GA | DCR | 2024-01-31 | 1 | X | X | X | X | X | 2025-07-30 | 2025-09-29 | 0.8 | Bld 14, CH comp 1-11 , 1-6 brackets installed
Fairfield - Arista Fairfield | Bike Racks | 14 | 28 | Pre Galv. Finish | GA | DTS | 2025-03-03 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-31 | O | 5 of 28 installed
Fairfield - Arista Fairfield | Bld 9 Balcony Rails | 95.8212 | 70.5 | Railing Black | GA | DCR | 2025-03-25 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-05 | O
Fairfield - Arista Fairfield | Bld 11 Balcony Rails | 84.9786 | 60.25 | Railing Black | GA | DCR | 2025-04-08 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-04 | O | QC Done
Fairfield - Arista Fairfield | Bldg 11 Roof Access Ladder | 3 | 3 | Railing Black | GA | SDO | 2025-04-11 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-30 | O | QC Done
Fairfield - Arista Fairfield | Bld 12 Stair 1-4 ,south stairs, cane rails | 25 | 20 | Railling Black 38/81009 | GA | CBA | 2025-05-14 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-31 | O | QC Done
Fairfield - Arista Fairfield | Remaining Balcony Rails | 50 | 0 | Railing Black | GA | DCR | 2025-05-23 | 1 | X | X | X | X | X | 2025-06-04 | 2025-06-04 | O | QC Done
Fairfield - Arista Fairfield | Bld 12 Balcony Rails | 138.9465 | 100.25 | Railing Black | GA | DCR | 2025-05-15 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-07 | O | QC Done
Fairfield - Arista Fairfield | Awning KP's | 10 | 0 | Railing Black | GA | DCR | 2025-04-23 | 1 | X | X | X | X | X | 2025-05-20 | 2025-05-20 | O | QC Done
Hinton - Metro Center | Bld 1 Balcony Guardrail | 88.25 | 88.25 | Railing Black | GA | DCR | 2025-01-16 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-06 | 0.5 | QC Done
Hinton - Metro Center | Stair Core 4A | 63.9284 | 61.65 | Red Oxide Primed | GA | DCR | 2025-02-28 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-04 | 0.9 | All but WHR
Hinton - Metro Center | Bld 2 Roof Access Ladder | 0 | 6.5 | Red Oxide Primed | GA | DCR | 2025-02-20 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-30 | O
Hinton - Metro Center | Stair Core 3A | 74.6101 | 73.6 | Red Oxide Primed | GA | DCR | 2024-09-16 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-05 | 0.9 | All but WHR
Hinton - Metro Center | Stair Core 3B | 72.6349 | 71.55 | Red Oxide Primed | GA | DCR | 2024-09-16 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-05 | 0.9 | All but WHR
Hinton - Metro Center | Stair Core 5B | 83.804 | 82.65 | Red Oxide Primed | GA | DCR | 2025-03-28 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-06 | 0.9 | All but WHR
Hinton - Metro Center | Stair Core 5A | 83.804 | 82.65 | Red Oxide Primed | GA | DCR | 2025-03-18 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-06 | 0.9 | All but WHR
Hinton - Metro Center | Stair Core 3B Lvl 1-2 | 35.8707 | 8 | Red Oxide Primed | GA | DCR | 2025-03-28 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-30 | 0.9 | All but WHR
Hinton - Metro Center | Stair Core 3A Lvl 1-2 | 30.7707 | 8 | Red Oxide Primed | GA | DCR | 2025-03-28 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-30 | 0.9 | All but WHR
Hinton - Metro Center | Stair Core 5C | 63.9284 | 61.65 | Red Oxide Primed | GA | DCR | 2024-12-24 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-04 | 0.9 | All but WHR
Hinton - Metro Center | Stair Core 4B | 64.178 | 63.4 | Red Oxide Primed | GA | DCR | 2024-12-23 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-04 | 0.9 | All but WHR
Hinton - Metro Center | Stair Core 1B | 64.178 | 63.4 | Red Oxide Primed | GA | DCR | 2024-06-05 | 1 | X | X | X | X | X | 2024-07-07 | 2024-07-10 | 0.9 | All but WHR
Hinton - Metro Center | Stair Core 1A | 64.178 | 63.4 | Red Oxide Primed | GA | DCR | 2024-06-05 | 1 | X | X | X | X | X | 2024-06-28 | 2024-07-03 | 0.9 | All but WHR
Hinton - Metro Center | Stair Core 2C | 64.178 | 63.4 | Red Oxide Primed | GA | DCR | 2024-09-16 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-04 | 0.9 | All but WHR
Hinton - Metro Center | Stair Core 3C | 64.178 | 63.4 | Red Oxide Primed | GA | DCR | 2024-09-16 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-04 | 0.9 | All but WHR
Hinton - Metro Center | Stair Core 2B | 68.0162 | 65.85 | Red Oxide Primed | GA | DCR | 2024-09-16 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-05 | 0.9 | All but WHR
Brinkman - Marshall Pointe | Elevator Hoist Beams | 10.73 | 0.1746 | Red Oxide Primed | GA | SDO | 2025-04-23 | 1 | X | X | X | X | X | 2025-05-14 | 2025-05-14 | O | QC Done
Garrett -Banyan High Point | Bld 2 Stair B | 38.702 | 38.1 | Red Oxide Primed | RL | DCR | 2024-12-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-01 | 0.9 | QC Done
Garrett -Banyan High Point | Bld 2 Stair A | 38.702 | 38.1 | Red Oxide Primed | RL | DCR | 2024-12-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-01 | 0.9 | QC Done
Garrett -Banyan High Point | Bld 6 Stair B | 38.702 | 38.1 | Red Oxide Primed | RL | DCR | 2024-12-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-01 | 0.9 | All but WHR
Garrett -Banyan High Point | Bld 3 Stair A | 38.702 | 38.1 | Red Oxide Primed | RL | DCR | 2024-12-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-01 | 0.9 | All but WHR
Garrett -Banyan High Point | Bld 3 Stair B | 38.702 | 38.1 | Red Oxide Primed | RL | DCR | 2024-12-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-01 | 0.9 | All but WHR
Garrett -Banyan High Point | Bld 6 Stair A | 38.702 | 38.1 | Red Oxide Primed | RL | DCR | 2024-12-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-01 | 0.9 | All but WHR
Garrett -Banyan High Point | Bld 5 Stair B | 38.702 | 38.1 | Red Oxide Primed | RL | DCR | 2024-12-06 | 1 | X | X | X | X | X | 2025-04-28 | 2025-04-30 | 0.9 | QC Done
Garrett -Banyan High Point | Bld 5 Stair A | 38.702 | 38.1 | Red Oxide Primed | RL | DCR | 2024-12-06 | 1 | X | X | X | X | X | 2025-04-25 | 2025-04-29 | 0.9 | All but WHR
Garrett -Banyan High Point | Bld 1 Stair A | 58.0654 | 57.25 | Red Oxide Primed | RL | DCR | 2024-12-05 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-04 | 0.9 | All but WHR
Garrett -Banyan High Point | Bld 1 Stair B | 60.7906 | 60.05 | Red Oxide Primed | RL | DCR | 2024-12-05 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-04 | 0.9 | All but WHR
Garrett -Banyan High Point | Bld 4 Stair A | 38.702 | 38.1 | Red Oxide Primed | RL | DCR | 2024-12-06 | 1 | X | X | X | X | X | 2025-02-10 | 2025-02-12 | 0.9 | All but WHR
Garrett -Banyan High Point | Bld 4 Stair B | 38.702 | 38.1 | Red Oxide Primed | RL | DCR | 2024-12-06 | 1 | X | X | X | X | X | 2025-02-10 | 2025-02-12 | 0.9 | All but WHR
Brinkmann - Aspendale Littleton Senior | Beam # 18 | 5 | 1.5 | Red Oxide Primer | RL | RL | 2025-06-09 | 1 | X | X | X | X | X | 2025-06-16 | 2025-06-16 | O | Fabrication Error. Beam ordered 6/9.
Brinkmann - Aspendale Littleton | Structural Steel | 275.7061 | 397.9245 | TBD | RL | DTS | 2025-03-04 | 1 | X | X | X | X | X | 2025-03-31 | 2025-05-02 | 0.9 | QC Done
Mountain West Contractors - Fieldhouse (Idaho Springs) | Building 3 Stair Core 5 | 53.6906 | 52.5 | Railing Black | RL | SDO | 2025-04-02 | 1 | X | X | X | X | X | 2025-04-29 | 2025-05-02 | 0.9 | All but WHR
Mountain West Contractors - Fieldhouse (Idaho Springs) | Building 3 Stair Core 6 | 77.3292 | 75.1 | Railing Black | RL | SDO | 2025-04-07 | 1 | X | X | X | X | X | 2025-04-29 | 2025-05-05 | 0.9 | All but WHR
Mountain West Contractors - Fieldhouse (Idaho Springs) | Building 2 Stair Core 3 | 53.978 | 52.55 | Railing Black | RL | SDO | 2025-04-16 | 1 | X | X | X | X | X | 2025-05-12 | 2025-05-15 | 0.9 | All but WHR
Mountain West Contractors - Fieldhouse (Idaho Springs) | Building 2 Stair Core 4 | 61.728 | 59.55 | Railing Black | RL | SDO | 2025-04-18 | 1 | X | X | X | X | X | 2025-05-12 | 2025-05-15 | 0.9 | All but WHR
Mountain West Contractors - Fieldhouse (Idaho Springs) | Building 1 Stair Core 1 | 35.9207 | 34.85 | Railing Black | RL | SDO | 2025-04-21 | 1 | X | X | X | X | X | 2025-05-28 | 2025-05-30 | 0.9 | All but WHR
Mountain West Contractors - Fieldhouse (Idaho Springs) | Building 1 Stair Core 2 | 43.102 | 41.55 | Railing Black | RL | SDO | 2025-04-21 | 1 | X | X | X | X | X | 2025-05-28 | 2025-05-30 | 0.9 | All but WHR
Arlington - Velo Interlocken | Elevator Pit Ladder | 31.5 | 28 | Red Oxide Primed | RL | SDO | 2025-01-27 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-31 | O | QC Done
Arlington - Velo Interlocken | Standpipe Protection | 75 | 60 | Red Oxide Primed | RL | DCR | 2025-05-05 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-04 | O
Arlington - Velo Interlocken | Bld 2 Balconies | 145.7248 | 124 | Railing Black | RL | DCR | 2024-11-19 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-08 | 0.9 | QC Done
Arlington - Velo Interlocken | Bld 3 Balconies | 147.087 | 122.5 | Railing Black | RL | DCR | 2025-02-03 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-08 | 0.75 | Wait to ship
Arlington - Velo Interlocken | Bld 4 Balconies | 147.4876 | 125.5 | Railing Black | RL | DCR | 2025-01-30 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-08 | 0.5 | Wait to ship
Arlington - Velo Interlocken | Bld 5 Stair Core 1 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-06 | 0.9 | All but WHR
Arlington - Velo Interlocken | Bld 5 Stair Core 2 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-06 | 0.9 | All but WHR
Arlington - Velo Interlocken | Bld 6 Stair Core 2 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2024-12-19 | 2024-12-26 | 0.9 | All but WHR
Arlington - Velo Interlocken | Bld 6 Stair Core 1 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2024-12-19 | 2024-12-26 | 0.9 | All but WHR
Arlington - Velo Interlocken | Bld 3 Stair Core 1 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2024-10-28 | 2024-11-04 | 0.9 | All but WHR
Arlington - Velo Interlocken | Bld 3 Stair Core 2 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2024-10-28 | 2024-11-04 | 0.9 | All but WHR
Arlington - Velo Interlocken | Bld 1 Stair Core 1 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-06 | 0.9 | All but WHR
Arlington - Velo Interlocken | Bld 1 Stair Core 2 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-06 | 0.9 | All but WHR
Arlington - Velo Interlocken | Bld 2 Stair Core 1 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2024-10-07 | 2024-10-14 | 0.9 | All but WHR
Arlington - Velo Interlocken | Bld 2 Stair Core 2 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2024-10-07 | 2024-10-14 | 0.9 | All but WHR
Arlington - Velo Interlocken | Bld 4 Stair Core 1 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-06 | 0.9 | All but WHR
Arlington - Velo Interlocken | Bld 4 Stair Core 2 | 73.8 | 83.45 | Red Oxide Primed | RL | DCR | 2024-08-06 | 1 | X | X | X | X | X | 2025-07-30 | 2025-08-06 | 0.9 | All but WHR
AMLI - Littleton Village II | Structural Framing at Leasing Fireplace | 7.5 | 8.3 | Red Oxide Primed | DR | FMW | 2025-05-21 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-30 | O | QC Done
Fairfield Development - Vista Highlands | Bld 15 Embeded posts | 0 | 3.1875 | Factory Black | GA | CBA | 2025-06-17 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-30 | O
Fairfield Development - Vista Highlands | Bld 14 Embeded posts | 0 | 2.2031 | Factory Black | GA | CBA | 2025-06-17 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-30 | O
Brinkman - Marshall Pointe | Garage Stair Core 1 Guard Rails | 40.825 | 38.825 | Red Oxide Primed | GA | CBA | 2025-05-29 | 1 | X | X | X | X | X | 2025-06-19 | 2025-06-23 | O
Garrett -Banyan High Point | Building 4 Roof Screen Frame | 31.472 | 28 | Railing Black 38/81009 | RL | CBA | 2025-05-28 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-31 | O | QC Done
Thompson Thrift - Stack at Wheat Ridge | Structural Steel Embeds | 0 | 0 | Raw Finish | DR | RJA | 2025-06-16 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-30 | O
Brinkman - Marshall Pointe | (1) Column Baseplate | 0.5 | 2 | Red Oxide Primed | GA | GA | 2025-06-17 | 1 | X | X | X | X | X | 2025-07-30 | 2025-07-30 | O
TCR - Alexan Diagonal | Bld 3 Patio Rails | 49 | 35 | Railing Black | DR | DCR | 2025-05-29 | 2 | X | X | X | X | T | 2025-07-30 | 2025-08-01 |  | QC Done
TCR - Alexan Diagonal | Bldg 1 Garage Screen East | 47.5 | 47.5 | Railing Black | DR | SDO | 2025-02-27 | 2 | X | X | X | X | T | 2025-07-30 | 2025-08-01 |  | QC Done
Thompson Thrift - Landing at Lemay | Building 2 Carraige house juliet | 0.5452 | 3.1726 | Factory Black | DR | CBA | 2025-04-29 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-30
Thompson Thrift - Landing at Lemay | Building 3 Carraige house juliet | 0.5452 | 3.1726 | Factory Black | DR | CBA | 2025-04-15 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-30
Thompson Thrift - Landing at Lemay | Bilding 6 Patio & Balcony Ultralox Rails P1 of 2 | 9.4564 | 110.0564 | Factory Balck | DR | CBA | 2025-05-02 | 2 | X | X | X | X | T | 2025-06-23 | 2025-07-01
Thompson Thrift - Landing at Lemay | Building 5 Carraige house juliet | 0.5452 | 3.1726 | Factory Black | DR | CBA | 2025-05-02 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-30
Thompson Thrift - Landing at Lemay | Building 4 Carraige house juliet | 0.5452 | 3.1726 | Factory Black | DR | CBA | 2025-05-02 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-30
Thompson Thrift - Landing at Lemay | Building 1 Middle Stair | 22.5 | 21 | Railing Black | DR | CBA | 2025-04-15 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-31
Thompson Thrift - Landing at Lemay | Building 1 West Stair | 22.5 | 21 | Railing Black | DR | CBA | 2025-04-01 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-31
Thompson Thrift - Landing at Lemay | Building 1 East Stair | 22.5 | 21 | Railing Black | DR | CBA | 2025-04-15 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-31
Thompson Thrift - Landing at Lemay | Building 6 East Stair | 22.5 | 21 | Railing Black | DR | CBA | 2025-05-06 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-31 |  | Powdered Waiting on 1 1/2 " SDS
AMLI - Littleton Village II | Stair Core B Guard Rails | 48.099 | 43.599 | Red Oxide Primed | DR | CBA | 2025-05-09 | 2 | X | X | X | X | T | 2025-07-30 | 2025-08-01 |  | QC Done
AMLI - Littleton Village II | Stair Core A Guard Rails | 65 | 59.25 | Red Oxide Primed | DR | CBA | 2025-05-22 | 2 | X | X | X | X | T | 2025-07-30 | 2025-08-04 |  | QC Done
Fairfield - Arista Fairfield | Bld 9 CMU Retaining Wall Guardrail North | 13.3 | 2 | Red Oxide Primed | GA | DCR | 2025-04-22 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-30 |  | QC Done
Fairfield - Arista Fairfield | Bldg 13 Roof Access Ladder | 3 | 3 | Red Oxide Primed | GA | CBA | 2025-05-28 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-30 |  | QC Done
Hinton - Metro Center | Bld 1 Stoop Landing Guardrails | 17.5 | 17.5 | Railing Black | GA | DCR | 2025-02-05 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-31 |  | QC Done
Hinton - Metro Center | Bld 3 Balcony Guardrail | 179.75 | 179.75 | Railing Black | GA | DCR | 2025-04-28 | 2 | X | X | X | X | T | 2025-07-30 | 2025-08-14 |  | QC Done
Hinton - Metro Center | Bld 2 Balcony East | 91.25 | 91.25 | Railing Black | GA | DCR | 2025-05-21 | 2 | X | X | X | X | T | 2025-07-30 | 2025-08-06 |  | QC Done
Hinton - Metro Center | Remaining Awning Clevis & Knife Plates | 10.5 | 0 | Red Oxide Primed | GA | DCR | 2025-05-29 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-30 |  | Clevis rods delivered 6/17
Hinton - Metro Center | Bld 4 Sky Lounge Standoffs | 0 | 0 | RAW | GA | DCR | 2025-06-09 | 2 | X | X | X | X | T | 2025-06-17 | 2025-06-17 |  | Only need (5)
Hinton - Metro Center | Bld 4 Roof Access Ladder | 3 | 3 | Red Oxide Primed | GA | DCR | 2025-06-02 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-30 |  | QC Done
PCL - 16th Street Mall | Planter Railing | 213 | 142 | Custom RAL 6033 (Mint) | GA | SDO | 2024-07-29 | 2 | X | X | X | X | O | 2025-07-30 | 2025-08-11
Brinkman - Marshall Pointe | Structural Columns & Beams Install Area C | 0 | 42.7375 | S.W. Epoxy Primer | GA | SDO | 2025-04-21 | 2 | X | X | X | X | T | 2025-07-30 | 2025-08-01
Brinkman - Marshall Pointe | Structural Columns & Beams Install Area D | 0 | 37.2 | S.W. Epoxy Primer | GA | SDO | 2025-04-21 | 2 | X | X | X | X | O | 2025-07-30 | 2025-08-01
Brinkman - Marshall Pointe | Structural Columns & Beams Install Area E | 0 | 14 | S.W. Epoxy Primer | GA | SDO | 2025-04-21 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Brinkman - Marshall Pointe | Structural Columns & Beams Install Area F | 0 | 45.8625 | S.W. Epoxy Primer | GA | SDO | 2025-04-21 | 2 | X | X | X | X | O | 2025-07-30 | 2025-08-01
Brinkman - Marshall Pointe | Structural Columns & Beams Install Area J | 0 | 4 | S.W. Epoxy Primer | GA | SDO | 2025-04-21 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Brinkman - Marshall Pointe | Structural Columns & Beams Install Area K | 0 | 4 | S.W. Epoxy Primer | GA | SDO | 2025-04-21 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Garrett -Banyan High Point | Building 1 Roof Screen Frame | 66.316 | 59 | Railling Black 38/81009 | RL | CBA | 2025-06-09 | 2 | X | X | X | X | O | 2025-07-30 | 2025-08-04
Garrett -Banyan High Point | Building 2 Roof Screen Frame | 66.316 | 59 | Railling Black 38/81009 | RL | CBA | 2025-06-09 | 2 | X | X | X | X | O | 2025-07-30 | 2025-08-04
Garrett -Banyan High Point | Building 3 Roof Screen Frame | 31.472 | 28 | Railling Black 38/81009 | RL | CBA | 2025-06-09 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
Garrett -Banyan High Point | Building 6 Roof Screen Frame | 31.472 | 28 | Railling Black 38/81009 | RL | CBA | 2025-06-09 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
Garrett -Banyan High Point | Building 5 Roof Screen Frame | 18.265 | 16.25 | Railling Black 38/81009 | RL | CBA | 2025-06-09 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
Brinkmann - Aspendale Littleton Senior | Roof Mechanical Screens Angles | 9.7125 | 97.125 | Red Oxide Primed | RL | CBA | 2025-05-27 | 2 | X | X | X | X | T | 2025-07-30 | 2025-08-07
Brinkmann - Aspendale Littleton Senior | Roof Access Ladder | 5 | 4 | Railing Black | RL | DCR | 2025-05-27 | 2 | X | X | X | X | T | 2025-07-30 | 2025-07-30
Evergreen - Outlook Green Valley Ranch | Bld 16 HD Embed Install | 0 | 15.05 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Evergreen - Outlook Green Valley Ranch | Bld 15 HD Embed Install | 0 | 17.5 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
Evergreen - Outlook Green Valley Ranch | Bld 14 HD Embed Install | 0 | 7 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Evergreen - Outlook Green Valley Ranch | Bld 13 HD Embed Install | 0 | 7 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Evergreen - Outlook Green Valley Ranch | Bld 12 HD Embed Install | 0 | 15.05 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Evergreen - Outlook Green Valley Ranch | Bld 11 HD Embed Install | 0 | 21 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
Evergreen - Outlook Green Valley Ranch | Bld 10 HD Embed Install | 0 | 15.05 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Evergreen - Outlook Green Valley Ranch | Bld 9 HD Embed Install | 0 | 17.5 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
Evergreen - Outlook Green Valley Ranch | Bld 8 HD Embed Install | 0 | 17.5 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
Evergreen - Outlook Green Valley Ranch | Bld 7 HD Embed Install | 0 | 17.5 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
Evergreen - Outlook Green Valley Ranch | Bld 6 HD Embed Install | 0 | 17.5 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
Evergreen - Outlook Green Valley Ranch | Bld 5 HD Embed Install | 0 | 17.5 | Raw | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
Evergreen - Outlook Green Valley Ranch | Bld 4 HD Embed Install | 0 | 7 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Evergreen - Outlook Green Valley Ranch | Bld 3 HD Embed Install | 0 | 7 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Evergreen - Outlook Green Valley Ranch | Bld 2 HD Embed Install | 0 | 17.5 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-31
Evergreen - Outlook Green Valley Ranch | Bld 1 HD Embed Install | 0 | 6.3 | RAW | RL | DCR | 2025-06-03 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Arlington - Velo Interlocken | Bld 5 Balconies | 147.087 | 122.5 | Railing Black | RL | DCR | 2025-02-10 | 2 | X | X | X | X | T | 2025-07-30 | 2025-08-08 |  | Wait to ship
Fairfield Development - Vista Highlands | Roof Access Ladder Type A Bld 4 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Fairfield Development - Vista Highlands | Roof Access Ladder Type A Bld 6 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Fairfield Development - Vista Highlands | Roof Access Ladder Type A Bld 7 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Fairfield Development - Vista Highlands | Roof Access Ladder Type A Bld 8 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Fairfield Development - Vista Highlands | Roof Access Ladder Type A Bld 9 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Fairfield Development - Vista Highlands | Roof Access Ladder Type A Bld 11 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Fairfield Development - Vista Highlands | Roof Access Ladder Type A Bld 14 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Fairfield Development - Vista Highlands | Roof Access Ladder Type B Bld 2 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Fairfield Development - Vista Highlands | Roof Access Ladder Type B Bld 3 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Fairfield Development - Vista Highlands | Roof Access Ladder Type B Bld 5 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Fairfield Development - Vista Highlands | Bld 13 Embeded posts | 0 | 2.9375 | Factory Black | GA | CBA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Fairfield Development - Vista Highlands | Bld 2 Embeded posts | 0 | 2.9375 | Factory Black | GA | CBA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Fairfield Development - Vista Highlands | Bld 4 Embeded posts | 0 | 2.2031 | Factory Black | GA | CBA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Fairfield Development - Vista Highlands | Bld 3 Embeded posts | 0 | 2.9375 | Factory Black | GA | CBA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Fairfield Development - Vista Highlands | Roof Access Ladder Type B Bld 12 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Fairfield Development - Vista Highlands | Roof Access Ladder Type B Bld 13 | 0 | 6 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Fairfield Development - Vista Highlands | Roof Access Ladder Type C Bld 10 | 0 | 9 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Fairfield Development - Vista Highlands | Roof Access Ladder Type C Bld 15 | 0 | 9 | Railing Black | GA | RJA | 2025-06-17 | 2 | X | X | X | X | O | 2025-07-30 | 2025-07-30
Garrett -Banyan High Point | Entrance Canopies | 143 | 256 | Red Oxide Primed | RL | CBA | 2025-01-08 | 4 | X | X | X | X | X | 2025-07-30 | 2025-08-21 | O | testing again
Arlington - Velo Interlocken | Bld 6 Balconies | 147.087 | 122.5 | Railing Black | RL | DCR | 2025-02-27 | 5 | X | X | X | O | T | 2025-07-30 | 2025-08-08 |  | QC Done
Hinton - Metro Center | Bld 2 Stoop Landing Guardrails | 70 | 70 | Railing Black | GA | DCR | 2025-02-28 | 6 | X | X | X | O | T | 2025-07-30 | 2025-08-05 |  | QC Done
Arlington - Velo Interlocken | Bottom Saddle Clips | 3.5 | 1 | Railing Black | RL | RL | 2025-04-15 | 7 | X | X | X | O |  | 2025-07-30 | 2025-07-30 |  | 50 are done
Thompson Thrift - Landing at Lemay | Building 6 West Stair | 22.5 | 21 | Railing Black 38/81009 | DR | CBA | 2025-05-02 | 8 | X | X | X | O | T | 2025-07-30 | 2025-07-31 |  | Rework done
Thompson Thrift - Landing at Lemay | Building 6 Middle Stair | 22.5 | 21 | Railing Black 38/81009 | DR | CBA | 2025-05-07 | 9 | X | X | X | O | T | 2025-07-30 | 2025-07-31 |  | Rework done
Brinkman - Marshall Pointe | Roof Screens | 147 | 392 | Raven Black | GA | RJA | 2025-05-15 | 10 | X | X | X | O | T | 2025-07-30 | 2025-09-02 |  | test mpte jaaaas
Brinkmann - Aspendale Littleton | Roof Mechanical Screens posts | 146.8125 | 195.75 | Red Oxide Primed | RL | CBA | 2025-05-23 | 11 | X | X | O |  |  | 2025-07-31 | 2025-08-18 |  | test note
Brinkman - Marshall Pointe | Structural Columns & Beams Leave Out Area A | 174.4598 | 116.4792 | 1 HR. intumescent | GA | CBA | 2025-06-04 | 12 | X | X | X | O | T | 2025-06-19 | 2025-06-30 |  | QC Done
AMLI - Littleton Village II | Structural Steel | 1050.5498 | 694.9416 | Primmed and Iutumescent | DR | DTS | 2025-05-27 | 13 | X | X | O |  |  | 2025-07-10 | 2025-09-09 |  | plates are here
Hinton - Kairoi (Tripoint) | WWM Screen Entrance Gates | 23.5 | 17 | BK247 | GA | DCR | 2025-04-03 | 14 | X | X | O |  | T | 2025-08-07 | 2025-08-08 |  | BK247 (off hold CO executed) mesh is here
Hinton - Metro Center | Bld 4 Ramp Rail | 23.5 | 22 | Railing Black | GA | DCR | 2025-06-03 | 15 | X | X | O |  | T | 2025-08-07 | 2025-08-08
Hinton - Kairoi (Tripoint) | Garage Fence | 115 | 98 | BK 247 | GA | DCR | 2025-06-03 | 16 | X | x | O |  |  | 2025-08-08 | 2025-08-18
Fairfield Development - Vista Highlands | Bld 15 Stair 1 Rails | 11.25 | 9 | TBD | GA | DCR | 2025-06-02 | 17 | X | X | X | O | T | 2025-08-08 | 2025-08-08 |  | QC Done
Fairfield Development - Vista Highlands | Bld 15 Stair 2 Rails | 11.25 | 9 | TBD | GA | DCR | 2025-06-02 | 18 | X | X | O |  |  | 2025-08-08 | 2025-08-08
Fairfield Development - Vista Highlands | Bld 15 Stair 3 Rails | 11.25 | 9 | TBD | GA | DCR | 2025-06-02 | 19 | X | X | O |  |  | 2025-08-08 | 2025-08-08
Brinkman - Marshall Pointe | Garage Stair Core 3 Guard Rails | 57 | 52.75 | Red Oxide Primed | GA | CBA | 2025-06-04 | 20 | X | X | HOLD |  |  | 2025-06-25 | 2025-06-30 |  | HOLD
TCR - Alexan Diagonal | Replacement Angles for Bike storage Fence |  |  | Railing Black 38/81009 | DR | DR | 2025-06-11 | 21 | X | O |  |  |  | 2025-06-17 | 2025-06-17 |  | HOT NEED ASAP. Waiting on new punch. Due 6/18
Brinkmann - Wind Crest RB3.5 | Site Rails | 24.7843 | 20.9718 | Statuary Bronze | DR | DCR | 2025-06-13 | 22 | X | O |  |  |  | 2025-06-24 | 2025-06-25
Macy Development - Bristol Pointe Apt. | Stair Tread Repair | 1.38 | 0 | Cardinal BR-23 | WO | DTS | 2025-06-18 | 23 | HOT |  |  |  |  | 2025-06-25 | 2025-06-25
Garrett -Banyan High Point | Trellis B | 45.6 | 46.6 | Red Oxide Primed | RL | FMW | 2025-06-03 | 40 | O |  |  |  |  | 2025-08-11 | 2025-08-13 |  | Need embeds done.
Garrett -Banyan High Point | Pool Courtyard Trellis | 67.5 | 68.5 | Red Oxide Primed | RL | FMW | 2025-06-03 | 41 | O |  |  |  |  | 2025-08-12 | 2025-08-18 |  | Need embeds done.
Fairfield Development - Vista Highlands | Bld 14 Stair 1 Rails | 11.25 | 9 | Railing Black | GA | DCR | 2025-06-05 | 25 | X | O |  |  |  | 2025-08-12 | 2025-08-12
Fairfield Development - Vista Highlands | Bld 14 Stair 2 Rails | 11.25 | 9 | Railing Black | GA | DCR | 2025-06-05 | 26 | X | O |  |  |  | 2025-08-12 | 2025-08-12
Brinkman - Marshall Pointe | CMU Angles | 16.64 | 33.28 | Red Oxide Primed | GA | CBA | 2025-06-09 | 27 | O |  |  |  | T | 2025-08-12 | 2025-08-14 |  | HOT
Hinton - Kairoi (Tripoint) | Garage Door Steel Frame Center | 10 | 10 | BK247 | GA | DTS | 2025-06-10 | 80 | O |  |  |  |  | 2025-06-26 | 2025-06-26 |  | STOP, SCOPE PULLED
Hinton - Kairoi (Tripoint) | Dog Park Fence | 45.5 | 91 | TBD | GA | DCR | 2025-06-10 | 28 | X | O |  |  |  | 2025-08-13 | 2025-08-20 |  | perf is here
Hinton - Kairoi (Tripoint) | Center Garage Fence | 81.5 | 69 | BK 247 | GA | DCR | 2025-06-12 | 29 | O |  |  |  |  | 2025-08-13 | 2025-08-19
TCR - Alexan Diagonal | Elevator Sump Pit Cover | 8 | 8 | Red Ox | DR | DCR | 2025-06-11 | 12.5 | X | X | X | O | T | 2025-08-13 | 2025-08-13
Arlington - Velo Interlocken | Maintenance Shed Rail | 2.5 | 1 | Railing Black | RL | DCR | 2025-06-12 | 34 | O |  |  |  |  | 2025-08-13 | 2025-08-13
140 ASR - Crestview | Sleek Fence Privacy Screens Phase 2 | 0.9 | 18 | Sleek Black | WO | DCR | 2025-06-13 | 33 | - |  |  |  |  | 2025-08-13 | 2025-08-14
Fairfield Development - Vista Highlands | Bulk Roof Ladder Pack | 90 | 0 | Railing Black | GA | RJA | 2025-06-17 | 32 | O |  |  |  |  | 2025-08-14 | 2025-08-14
Mountain West Contractors - Dublin Springs | Balcony Rails | 245.9312 | 281 | Railing Black | GA | DCR | 2025-06-18 | 31 | HOT |  |  |  |  | 2025-07-03 | 2025-07-28
AMLI - Littleton Village II | Structural Intumescent Paint | 0 | 174.7 | Intumescent Paint | DR | DTS | 2025-05-29 | 80.555 | - |  |  |  |  | 2025-08-19 | 2025-09-02
Garrett -Banyan High Point | Bld 4 Balcony Rails | 132.7736 | 118 | Railing Black | RL | DCR | 2025-06-18 | 80.555 | - |  |  |  |  | 2025-08-20 | 2025-08-29
Arlington - Velo Interlocken | Bld 1 4th Floor Corner Balconies | 10 | 8.5 | Railing Black | RL | DCR | 2025-06-18 | 80.555 | - |  |  |  |  | 2025-08-20 | 2025-08-20
Garrett -Banyan High Point | Building 1 Canopy | 0 | 13.3333 | Red Oxide Primed | RL | CBA | 2025-06-19 | 80.555 | X | X | X | X | O | 2025-08-20 | 2025-08-20
Garrett -Banyan High Point | Building 1 Canopy Plates | 0 | 26.6667 | Red Oxide Primed | RL | CBA | 2025-06-19 | 80.555 | X | X | X | X | O | 2025-08-20 | 2025-08-21
Garrett -Banyan High Point | Building 2 Canopy | 0 | 8 | Red Oxide Primed | RL | CBA | 2025-06-19 | 80.555 | X | X | X | X | O | 2025-08-20 | 2025-08-20
Garrett -Banyan High Point | Building 2 Canopy Plates | 0 | 16 | Red Oxide Primed | RL | CBA | 2025-06-19 | 80.555 | X | X | X | X | O | 2025-08-20 | 2025-08-21
Garrett -Banyan High Point | Building 3 Canopy | 0 | 16 | Red Oxide Primed | RL | CBA | 2025-06-19 | 80.555 | X | X | X | X | O | 2025-08-20 | 2025-08-21
Garrett -Banyan High Point | Building 3 Canopy Plates | 0 | 32 | Red Oxide Primed | RL | CBA | 2025-06-19 | 80.555 | X | X | X | X | O | 2025-08-20 | 2025-08-22
Garrett -Banyan High Point | Building 5 Canopy | 0 | 16 | Red Oxide Primed | RL | CBA | 2025-06-19 | 80.555 | X | X | X | X | O | 2025-08-20 | 2025-08-21
Garrett -Banyan High Point | Building 5 Canopy Plates | 0 | 32 | Red Oxide Primed | RL | CBA | 2025-06-19 | 80.555 | X | X | X | X | O | 2025-08-20 | 2025-08-22
Garrett -Banyan High Point | Building 6 Canopy | 0 | 16 | Red Oxide Primed | RL | CBA | 2025-06-19 | 80.555 | X | X | X | X | O | 2025-08-20 | 2025-08-21
Garrett -Banyan High Point | Building 6 Canopy Plates | 0 | 32 | Red Oxide Primed | RL | CBA | 2025-06-19 | 80.555 | X | X | X | X | O | 2025-08-20 | 2025-08-22
Hinton - Metro Center | Bld 3 Stair & Ramp Rails North | 12.5 | 10 | Red Oxide Primed | GA | DCR | 2025-06-19 | 80.555 | - |  |  |  |  | 2025-08-20 | 2025-08-20
Hinton - Metro Center | Bld 3 Stair & Ramp Rails South | 17.5 | 14 | Red Oxide Primed | GA | DCR | 2025-06-19 | 80.555 | - |  |  |  |  | 2025-08-20 | 2025-08-20
[8 empty] | 80.555 | - |  |  |  |  | 2025-08-20
[8 empty] | 80.555 | - |  |  |  |  | 2025-08-20
[8 empty] | 80.555 | - |  |  |  |  | 2025-08-20
[8 empty] | 80.555 | - |  |  |  |  | 2025-08-20