## Submittals
Submittals Id | Project Number | Project Name | Title | Ball In Court Due Date | Final Due Date | Status | Type | Ball In Court | Response | Submittal Manager
63956218 | 480 | Alta Flatirons | Structural Steel Beams | 2025-11-16 | 2025-11-16 | Open | Submittal For Gc Approval | Bill O'Neill | Approved, Approved, Pending, For Record Only | Gary Almeida
64452445 | 999 | Misc. Project MHMW | Wyobraska Vet sign | 2025-07-27 | 2025-08-01 | Open | Submittal For Gc Approval | Bill O'Neill | Approved, Revise and Resubmit, For Record Only, Approved, Pending, Approved, Pending | Bill O'Neill
65206107 | 999 | Misc. Project MHMW | MHMW new location | 2025-11-16 | 2025-12-06 | Open | Submittal For Gc Approval | Bill O'Neill | Revise and Resubmit, For Record Only, Revise and Resubmit, Approved, Approved, Approved, Approved as Noted, For Record Only, Approved, For Record Only, Revise and Resubmit, Revise and Resubmit, Pending, Pending, Pending, Pending, Pending, Pending | Bill O'Neill
57913056 | 340 | Littleton Village II | Add Alternate Unit Budget - Countertop Support Brackets | 2025-02-24 | 2025-03-01 | Open | Submittal For Gc Approval | Danny Riddell | Approved, Pending, Approved as Noted, Pending | Danny Riddell
57913057 | 340 | Littleton Village II | Add Alternate - Bike Racks | 2025-01-20 | 2025-01-20 | Open | Submittal For Gc Approval | Danny Riddell | Approved, Approved, Approved, Pending | Danny Riddell
63012208 | 340 | Littleton Village II | Drink Ledge at Pool Courtyard | 2025-05-10 | 2025-05-20 | Open | Submittal For Gc Approval | Danny Riddell | Approved, For Record Only, Pending, Pending, Pending, Pending | Danny Riddell
63408742 | 340 | Littleton Village II | Garage Parapet & OSHA Railing | 2025-05-25 | 2025-06-14 | Open | Drafting Release Review | Danny Riddell | Pending, Forwarded For Review, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
65338470 | 450 | Sandstone Ranch | Roof Hatch Access Ladder and Security Gate |  | 2025-08-24 | Open | Submittal For Gc Approval | Danny Riddell | For Record Only, Revise and Resubmit, Revise and Resubmit, For Record Only, Approved | Danny Riddell
66445526 | 530 | 530- East Oak Townhomes | Stair Stringers @ Level 2 to Level 3 at Each Unit | 2025-10-28 | 2025-12-07 | Open | Submittal For Gc Approval | Danny Riddell | Approved, Approved, Pending, Revise and Resubmit, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
66445558 | 530 | 530- East Oak Townhomes | Balcony Guardrails | 2025-10-26 | 2025-12-05 | Open | Submittal For Gc Approval | Danny Riddell | Approved, Pending, Revise and Resubmit, Approved, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
66445651 | 530 | 530- East Oak Townhomes | Steel Handrail @ Level 4 Parapet | 2025-10-15 | 2025-11-04 | Open | Submittal For Gc Approval | Danny Riddell | For Record Only, Revise and Resubmit, Pending, Revise and Resubmit, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
66445719 | 530 | 530- East Oak Townhomes | Unit type A/C porch handrail | 2025-10-11 | 2025-10-31 | Open | Submittal For Gc Approval | Danny Riddell | For Record Only, Approved as Noted, Pending, Revise and Resubmit, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
66445736 | 530 | 530- East Oak Townhomes | Roof Access Ladder and Gate | 2025-11-09 | 2025-12-19 | Open | Submittal For Gc Approval | Danny Riddell | Approved, Pending, Revise and Resubmit, Revise and Resubmit, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
66445770 | 530 | 530- East Oak Townhomes | Bay Window Steel Framing | 2025-10-22 | 2025-12-01 | Open | Submittal For Gc Approval | Danny Riddell | Approved, Pending, Approved, Approved as Noted, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
66676595 | 530 | 530- East Oak Townhomes | Sun Shade Structure | 2025-11-16 | 2025-11-26 | Open | Submittal For Gc Approval | Danny Riddell | For Record Only, Revise and Resubmit, For Record Only, Pending, Pending, Pending, Pending, Pending | Danny Riddell
66838267 | 450 | Sandstone Ranch | Low Metal Canopy at 2nd levels only | 2025-10-22 | 2025-11-21 | Open | Submittal For Gc Approval | Danny Riddell | Approved, Pending, Revise and Resubmit, Revise and Resubmit, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
66838594 | 450 | Sandstone Ranch | High Metal Canopy with slat infill | 2025-10-22 | 2025-11-21 | Open | Submittal For Gc Approval | Danny Riddell | Approved, Pending, Revise and Resubmit, Approved, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
67118337 | 340 | Littleton Village II | Hanging Brick Relief at Storefront | 2025-11-16 | 2025-11-21 | Open | Drafting Release Review | Danny Riddell | Approved, Approved as Noted, Approved as Noted, Revise and Resubmit, Approved, Revise and Resubmit, Approved, Pending, Pending | Danny Riddell
67336093 | 450 | Sandstone Ranch | Retaining Wall West Elevation | 2025-11-15 | 2025-11-30 | Open | Drafting Release Review | Danny Riddell | Approved, Pending, Approved as Noted, Approved as Noted, Pending, Pending, Pending | Danny Riddell
61724059 | 380 | Marshall Pointe | Ramp Railings | 2025-11-12 | 2025-11-17 | Open | Drafting Release Review | Brian Panning | Approved as Noted, Approved, Revise and Resubmit, For Record Only, For Record Only, For Record Only, Revise and Resubmit, For Record Only, Approved, Pending, Pending | Gary Almeida
65884436 | 490 | Capital Hill | Stair Cores | 2025-11-04 | 2025-11-09 | Open | Submittal For Gc Approval | Brian Panning | Approved as Noted, Approved, Approved, Approved, Approved, Revise and Resubmit, Approved, For Record Only, Pending, Pending | Gary Almeida
65112007 | 500 | Novel Flatiron Crossing | Amenity Steel | 2025-08-05 | 2025-08-15 | Open | Submittal For Gc Approval | David Servold | Pending, Pending, Pending | Gary Almeida
66109564 | 410 | Columbine Square | Building 4 Structural Steel Package | 2025-10-11 | 2025-10-21 | Open | Drafting Release Review | David Servold | For Record Only, Approved as Noted, Pending, Approved as Noted, Pending, Pending, Pending | Rich Losasso
66109641 | 410 | Columbine Square | Building 4 Structural Embed Package | 2025-10-11 | 2025-10-21 | Open | Drafting Release Review | David Servold | For Record Only, Approved as Noted, Pending, Approved, Pending, Pending, Pending | Rich Losasso
66156110 | 410 | Columbine Square | Building 6 Structural Embed Package | 2025-11-08 | 2025-11-13 | Open | Drafting Release Review | David Servold | For Record Only, Approved as Noted, Approved, Revise and Resubmit, For Record Only, Approved, Pending, Pending | Rich Losasso
66676595 | 530 | 530- East Oak Townhomes | Sun Shade Structure | 2025-11-16 | 2025-11-26 | Open | Submittal For Gc Approval | David Servold | For Record Only, Revise and Resubmit, For Record Only, Pending, Pending, Pending, Pending, Pending | Danny Riddell
67308034 | 290 | Martin Residence | Interior guard rail | 2025-11-10 | 2025-11-15 | Open | Submittal For Gc Approval | David Servold | Pending, Pending, Pending | Gary Almeida
60714842 | 390 | Heritage on Hover | Stair Rails | 2025-11-08 | 2025-11-23 | Open | Submittal For Gc Approval | Colton Arendt | Approved, For Record Only, Revise and Resubmit, Approved, Revise and Resubmit, Pending, Pending, Pending, Pending | Rich Losasso
61749099 | 290 | Martin Residence | Interior Stair | 2025-03-18 | 2025-04-02 | Open | Submittal For Gc Approval | Colton Arendt | Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
65961512 | 330 | Aspendale Littleton (Headwaters) | Courtyard Trellis (Ownership) | 2025-11-08 | 2025-11-18 | Open | Submittal For Gc Approval | Colton Arendt | Revise and Resubmit, Approved, Revise and Resubmit, Pending, Pending, Pending | Rich Losasso
66445618 | 530 | 530- East Oak Townhomes | Level 1 Patio Privacy Screen | 2025-10-07 | 2025-11-21 | Open | Submittal For Gc Approval | Colton Arendt | Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
66854819 | 380 | Marshall Pointe | NorthEast Exterior Balconies | 2025-10-20 | 2025-10-30 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Gary Almeida
66854834 | 380 | Marshall Pointe | NorthWest Exterior Balconies | 2025-10-20 | 2025-10-30 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Gary Almeida
66927442 | 190 | Metro Center | CO#23 - Sidewalk Chase Covers | 2025-11-02 | 2025-11-07 | Open | Submittal For Gc Approval | Colton Arendt | Approved, Revise and Resubmit, Revise and Resubmit, For Record Only, Revise and Resubmit, Pending, Pending, Pending | Gary Almeida
67123356 | 900 | Velo Interlocken | Drainage Rails ( EZ Excavating) | 2025-11-02 | 2025-11-17 | Open | Submittal For Gc Approval | Colton Arendt | Pending, Pending, Pending, Pending, Pending, Pending | Rich Losasso
67152419 | 500 | Novel Flatiron Crossing | Non-Bearing CMU Partition Bracing Embeds and Angles | 2025-11-03 | 2025-11-13 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending, Pending | Gary Almeida
67184837 | 380 | Marshall Pointe | MHMW CO#17 - Garage Low Wall Railing | 2025-11-04 | 2025-11-19 | Open | Submittal For Gc Approval | Colton Arendt | Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
67249416 | 330 | Aspendale Littleton (Headwaters) | Covered Walkway Steel | 2025-11-08 | 2025-11-23 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67269119 | 370 | Vista Highlands | Bld 9 Balconies | 2025-11-09 | 2025-11-19 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending, Pending | Gary Almeida
67269128 | 370 | Vista Highlands | Bld 10 Balconies | 2025-11-09 | 2025-11-19 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending, Pending | Gary Almeida
67269134 | 370 | Vista Highlands | Bld 11 Balconies | 2025-11-09 | 2025-11-19 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending, Pending | Gary Almeida
67269153 | 370 | Vista Highlands | Bld 12 Balconies | 2025-11-09 | 2025-11-19 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending, Pending | Gary Almeida
67300445 | 999 | Misc. Project MHMW | Compactor Shading | 2025-11-10 | 2025-11-25 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67303541 | 410 | Columbine Square | Building 2 stair core 1 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67303582 | 410 | Columbine Square | Building 2 stair core 2 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67303661 | 410 | Columbine Square | Building 2 stair core 3 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67303715 | 410 | Columbine Square | Building 4 stair core 1 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67303825 | 410 | Columbine Square | Building 4 stair core 2 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67303926 | 410 | Columbine Square | Building 5 stair core 1 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67303960 | 410 | Columbine Square | Building 5 stair core 2 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67304001 | 410 | Columbine Square | Building 5 stair core 3 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67304038 | 410 | Columbine Square | Building 6 stair core 1 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67304068 | 410 | Columbine Square | Building 6 stair core 2 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67304230 | 410 | Columbine Square | Building 7 stair core 1 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67304303 | 410 | Columbine Square | Building 7 stair core 2 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67304570 | 410 | Columbine Square | Building 7 stair core 3 | 2025-11-10 | 2025-11-14 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67336301 | 450 | Sandstone Ranch | Fitness Stair | 2025-11-11 | 2025-12-01 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
67336370 | 320 | 320 Landing at Lemay | Building #16 South Stair | 2025-11-11 | 2025-12-01 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
67336442 | 320 | 320 Landing at Lemay | Building #16 North Stair | 2025-11-11 | 2025-12-01 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
67336553 | 320 | 320 Landing at Lemay | Building #16 Balcony and Patio Rails | 2025-11-11 | 2025-12-01 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
67403274 | 900 | Velo Interlocken | Clubhouse Exterior Rail | 2025-11-15 | 2025-11-30 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67434306 | 440 | Outlook Green Valley Ranch | Building 6 Post Install | 2025-11-16 | 2025-11-21 | Open | Drafting Release Review | Colton Arendt | Approved, Approved, Pending, Pending | Rich Losasso
67434336 | 440 | Outlook Green Valley Ranch | Building 6 Rail Install | 2025-11-16 | 2025-12-01 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67434372 | 440 | Outlook Green Valley Ranch | Building 7 Post Install | 2025-11-16 | 2025-12-01 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67434390 | 440 | Outlook Green Valley Ranch | Building 7 Rail Install | 2025-11-16 | 2025-12-01 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67434413 | 440 | Outlook Green Valley Ranch | Building 8 Post Install | 2025-11-16 | 2025-12-01 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
67434435 | 440 | Outlook Green Valley Ranch | Building 8 Rail Install | 2025-11-16 | 2025-12-01 | Open | Drafting Release Review | Colton Arendt | Pending, Pending, Pending, Pending | Rich Losasso
63956243 | 480 | Alta Flatirons | ADD/ALT Open Space Shade Structure | 2025-07-01 | 2025-08-10 | Open | Submittal For Gc Approval | Gary Almeida | For Record Only, Revise and Resubmit, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
63956244 | 480 | Alta Flatirons | ADD/ALT Standard Bike Rack | 2025-06-26 | 2025-08-08 | Open | Submittal For Gc Approval | Gary Almeida | Forwarded For Review, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
64744482 | 470 | Olde Course Maintenance Building | Stair to Mezzanine | 2025-11-08 | 2025-11-23 | Open | Drafting Release Review | Gary Almeida | For Record Only, Approved, Revise and Resubmit, For Record Only, For Record Only, Approved, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
66212434 | 370 | Vista Highlands | CO#03 - Trellis A | 2025-09-24 | 2025-10-19 | Open | Drafting Release Review | Gary Almeida | Forwarded For Review, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
65206107 | 999 | Misc. Project MHMW | MHMW new location | 2025-11-16 | 2025-12-06 | Open | Submittal For Gc Approval | Luis Solano | Revise and Resubmit, For Record Only, Revise and Resubmit, Approved, Approved, Approved, Approved as Noted, For Record Only, Approved, For Record Only, Revise and Resubmit, Revise and Resubmit, Pending, Pending, Pending, Pending, Pending, Pending | Bill O'Neill
65961346 | 330 | Aspendale Littleton (Headwaters) | Covered Walkway | 2025-11-15 | 2025-11-25 | Open | Submittal For Gc Approval | Rich Losasso | Approved, Approved, Revise and Resubmit, Approved, For Record Only, Revise and Resubmit, Approved, Pending, Approved, Pending, Pending | Rich Losasso
66110509 | 390 | Heritage on Hover | Building A West Core | 2025-09-20 | 2025-10-05 | Open | Drafting Release Review | Rich Losasso | Forwarded For Review, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Rich Losasso
66110537 | 390 | Heritage on Hover | Building A East Core | 2025-09-20 | 2025-10-05 | Open | Drafting Release Review | Rich Losasso | Forwarded For Review, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Rich Losasso
66788515 | 440 | Outlook Green Valley Ranch | Building 5 Balcony Rail Install | 2025-11-11 | 2025-11-21 | Open | Drafting Release Review | Rich Losasso | Approved, Pending, Pending, Pending | Rich Losasso
66885801 | 510 | Idaho Springs Police Station | Eastside Structural Steel | 2025-11-08 | 2025-11-08 | Open | Submittal For Gc Approval | Rich Losasso | Approved, Revise and Resubmit, Approved, Pending | Rich Losasso
66885964 | 510 | Idaho Springs Police Station | Westside Structural Steel | 2025-11-12 | 2025-11-22 | Open | Submittal For Gc Approval | Rich Losasso | Approved, Revise and Resubmit, For Record Only, For Record Only, Pending, Pending, Pending | Rich Losasso
63325703 | 370 | Vista Highlands | bld 2 stair | 2025-05-21 | 2025-05-31 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending, Pending, Pending | Gary Almeida
64951508 | 290 | Martin Residence | Front Entry Trellis Steel Framing | 2025-07-29 | 2025-08-08 | Open | Drafting Release Review | Dalton Rauer | Pending, For Record Only, Pending, Pending, Pending | Gary Almeida
65111996 | 500 | Novel Flatiron Crossing | Stair Cores #01 | 2025-08-31 | 2025-10-09 | Open | Submittal For Gc Approval | Dalton Rauer | Pending, Approved, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
65111997 | 500 | Novel Flatiron Crossing | Stair Core #02 | 2025-08-31 | 2025-10-09 | Open | Submittal For Gc Approval | Dalton Rauer | Approved, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
65112011 | 500 | Novel Flatiron Crossing | Stair #02 Vestibule Canopy | 2025-08-13 | 2025-09-21 | Open | Submittal For Gc Approval | Dalton Rauer | For Record Only, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
65112024 | 500 | Novel Flatiron Crossing | Loose Lintels | 2025-11-16 | 2025-12-21 | Open | Submittal For Gc Approval | Dalton Rauer | For Record Only, For Record Only, For Record Only, For Record Only, Final PDF Pack, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
65619027 | 370 | Vista Highlands | Bld 6 Stair | 2025-08-27 | 2025-09-06 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending | Gary Almeida
65836286 | 500 | Novel Flatiron Crossing | Brick Relief Angle | 2025-09-21 | 2025-09-26 | Open | Submittal For Gc Approval | Dalton Rauer | Pending, For Record Only, Pending, Pending | Gary Almeida
66088021 | 190 | Metro Center | Bld 5 Balconies | 2025-09-20 | 2025-09-30 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending, Pending | Gary Almeida
66196163 | 370 | Vista Highlands | Bld 8 Stairs | 2025-09-23 | 2025-10-03 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending | Gary Almeida
66196168 | 370 | Vista Highlands | Bld 7 Stairs | 2025-09-23 | 2025-10-03 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending | Gary Almeida
66198859 | 190 | Metro Center | Bld 5 Roof access Ladder | 2025-09-23 | 2025-10-03 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending | Gary Almeida
66791943 | 170 | Banyan High Point | Building 6 Balcony Rails | 2025-10-18 | 2025-11-02 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending, Pending | Rich Losasso
67124398 | 500 | Novel Flatiron Crossing | Site embeds | 2025-11-02 | 2025-11-17 | Open | Submittal For Gc Approval | Dalton Rauer | Rejected, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
67269208 | 370 | Vista Highlands | Bld 9 Stair WHG | 2025-11-09 | 2025-11-19 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending, Pending, Pending | Gary Almeida
67269216 | 370 | Vista Highlands | Bld 10 Stair WHG | 2025-11-09 | 2025-11-19 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending, Pending, Pending | Gary Almeida
67269224 | 370 | Vista Highlands | Bld 11 Stair WHG | 2025-11-09 | 2025-11-19 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending, Pending, Pending | Gary Almeida
67269231 | 370 | Vista Highlands | Bld 12 Stair WHG | 2025-11-09 | 2025-11-19 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending, Pending, Pending | Gary Almeida
67336086 | 190 | Metro Center | Bld 2 interior Ramps | 2025-11-11 | 2025-11-21 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending, Pending | Gary Almeida
67400030 | 340 | Littleton Village II | Commercial Awnings | 2025-11-15 | 2025-12-05 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending, Pending, Pending, Pending, Pending | Danny Riddell
67442869 | 900 | Velo Interlocken | 12" Returns Bldg 2 | 2025-11-16 | 2025-12-01 | Open | Drafting Release Review | Dalton Rauer | Pending, Pending, Pending, Pending | Rich Losasso
66685313 | 480 | Alta Flatirons | Structural Steel Columns Embeds | 2025-10-13 | 2025-11-27 | Open | Submittal For Gc Approval | Dominic Wenk | Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
60670523 | 380 | Marshall Pointe | Garage Pipe Protections | 2025-11-09 | 2025-11-19 | Open | Drafting Release Review | Rourke Alvarado | For Record Only, Pending, Pending, Pending, Pending | Gary Almeida
61723622 | 380 | Marshall Pointe | Garage Ramp Railings | 2025-11-16 | 2025-12-06 | Open | Drafting Release Review | Rourke Alvarado | Approved as Noted, Approved, Pending, Pending, Pending, Pending, Pending, Pending, Pending | Gary Almeida
66156160 | 410 | Columbine Square | Building 6 Structural Steel Package | 2025-11-01 | 2025-11-06 | Open | Drafting Release Review | Rourke Alvarado | For Record Only, Approved, Approved as Noted, Approved as Noted, Pending, Pending, Pending | Rich Losasso
67138506 | 370 | Vista Highlands | Bld 14 Trash Enclosure Gates | 2025-11-02 | 2025-11-12 | Open | Drafting Release Review | Rourke Alvarado | Pending, Pending, Pending, Pending | Gary Almeida
67257375 | 410 | Columbine Square | Trash Enclosure Bollards Only | 2025-11-08 | 2025-11-23 | Open | Drafting Release Review | Dustin Pauley | Pending, Pending, Pending, Pending | Rich Losasso